## Cost Allocation Oct
|  | 2018 | [5 empty] | 2018 | [5 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021
| Cost Allocation Development | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Sep 2018 update | Stakeholder engagement (completed)
Define time periods and time period weightings
Develop rates
Prepare filing
AUC review
|  | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021
| Capacity Cost Allocation Development | Q1 Jan: Q1; Q2 Apr: Q2; Q3 Jul: Q3; Q4 Oct: Q4; Q1 Jan: Q1; Q2 Apr: Q2; Q3 Jul: Q3; Q4 Oct: Q4; Q1 Jan: Q1; Q2 Apr: Q2; Q3 Jul: Q3; Q4 Oct: Q4; Q1 Jan: Q1; Q2 Apr: Q2; Q3 Jul: Q3; Q4 Oct: Q4
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Oct 2018 update | Stakeholder engagement (completed)
Determine analysis scope, approach, schedule
Define time periods and time period weightings
Determine rate classes
Develop Weighted Energy Method rates
Develop self-supply / incentive rates
Prepare filing
|  | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021
| Transmission Cost Allocation Development | Q1 Jan: Q1; Q2 Apr: Q2; Q3 Jul: Q3; Q4 Oct: Q4; Q1 Jan: Q1; Q2 Apr: Q2; Q3 Jul: Q3; Q4 Oct: Q4; Q1 Jan: Q1; Q2 Apr: Q2; Q3 Jul: Q3; Q4 Oct: Q4; Q1 Jan: Q1; Q2 Apr: Q2; Q3 Jul: Q3; Q4 Oct: Q4
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Oct 2018 update | Stakeholder engagement (completed)
Determine analysis scope, approach, schedule
Historical data collection
Develop forecasts
Develop functionalization methods
Develop classifications
Determine cost allocations (rate classes)
Develop billing determinants
Design rates
Develop bill estimates & mitigation (if required)
Prepare filing
Weighted energy method weightings defined
Actively being worked on
Tariff Design Advisory Group formed
AUC final approval (est.)
Rates defined
Cost allocation filing submitted
Oct 9
Weighted energy method time periods defined
Weighted energy method time periods defined
AUC final approval (est.)
Weighted energy method weightings defined
Actively being worked on
Capacity Cost allocation filing submitted
Oct 9
Actively being worked on
Transission Cost allocation filing submitted
Oct 9

## Cost Allocation Nov
|  | 2018 | [5 empty] | 2018 | [5 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021
| Cost Allocation Development | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Sep 2018 update | Stakeholder engagement (completed)
Define time periods and time period weightings
Develop rates
Prepare filing
AUC review
|  | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021
| Capacity Cost Allocation Development | Q1 Jan: Q1; Q2 Apr: Q2; Q3 Jul: Q3; Q4 Oct: Q4; Q1 Jan: Q1; Q2 Apr: Q2; Q3 Jul: Q3; Q4 Oct: Q4; Q1 Jan: Q1; Q2 Apr: Q2; Q3 Jul: Q3; Q4 Oct: Q4; Q1 Jan: Q1; Q2 Apr: Q2; Q3 Jul: Q3; Q4 Oct: Q4
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Nov 2018 update | Stakeholder engagement (completed)
Determine analysis scope, approach, schedule
Define time periods and time period weightings
Determine rate classes
Develop Weighted Energy Method rates
Develop self-supply / incentive rates
Prepare filing
|  | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021
| Transmission Cost Allocation Development | Q1 Jan: Q1; Q2 Apr: Q2; Q3 Jul: Q3; Q4 Oct: Q4; Q1 Jan: Q1; Q2 Apr: Q2; Q3 Jul: Q3; Q4 Oct: Q4; Q1 Jan: Q1; Q2 Apr: Q2; Q3 Jul: Q3; Q4 Oct: Q4; Q1 Jan: Q1; Q2 Apr: Q2; Q3 Jul: Q3; Q4 Oct: Q4
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Nov 2018 update | Stakeholder engagement (completed)
Determine analysis scope, approach, schedule
Historical data collection
Develop forecasts
Develop functionalization methods
Develop classifications
Determine cost allocations (rate classes)
Develop billing determinants
Design rates
Develop bill estimates & mitigation (if required)
Prepare filing
Weighted energy method weightings defined
Actively being worked on
Tariff Design Advisory Group formed
AUC final approval (est.)
Rates defined
Cost allocation filing submitted
Oct 9
Weighted energy method time periods defined
Weighted energy method time periods defined
AUC final approval (est.)
Weighted energy method weightings defined
Actively being worked on
Capacity Cost allocation filing submitted
Nov 9
Actively being worked on
Transission Cost allocation filing submitted
Nov 9