## AESO Connection Pro - Data List
Project | Subproject | Project Type | Planning Area | STS MW Change | DTS MW Change | MW Type | Process Stage | Planned ISD | Applied On | Entered Queue
P0513 Pteragen Peace Butte Wind Farm | 1 | Connection | 4-Medicine Hat | 119.7 | 0.1 | Wind | 5 | 2019-12-01 16:00 | 2005-10-14 | 2010-08-31 06:00
P0462 Enel Alberta Castle Rock Wind Farm | 2 | Connection | 53-Fort Macleod | 30.6 | 0 | Wind | 5 | 2019-06-30 16:00 | 2005-01-05 | 2010-08-31 06:00
P0479 Naturener Wild Rose 1 Wind Farm | 1 | Connection | 4-Medicine Hat | 217.6 | 4 | Wind | 5 | 2019-07-15 16:00 | 2005-05-12 | 2010-08-31 06:00
P0515 Heritage Wind Energy Centre | 1 | Connection | 53-Fort Macleod | 300 | 0 | Wind | 3 | 2020-09-01 16:00 | 2005-09-22 | 2010-08-31 06:00
P0524 Enel Alberta Riverview Wind Farm | 1 | Connection | 53-Fort Macleod | 115 | 1 | Wind | 4 | 2019-06-30 | 2006-01-25 | 2010-08-31 06:00
P0580 Windy Point WAGF | 1 | Connection | 53-Fort Macleod | 63 | 0.6 | Wind | 4 | 2020-10-01 16:00 | 2006-05-12 | 2010-08-31 06:00
P0635 Suncor Hand Hills Wind Energy Project | 1 | Connection | 42-Hanna | 80 | 0.1 | Wind | 5 | 2019-09-01 16:00 | 2006-10-06 | 2010-08-31 06:00
P0678 BluEarth Hand Hills Wind Project | 1 | Connection | 42-Hanna | 78.2 | 0 | Wind | 5 | 2020-09-01 16:00 | 2007-01-15 | 2010-08-31 06:00
P0693 Naturener Wild Rose 2 Wind Farm | 1 | Connection | 4-Medicine Hat | 192 | 4 | Wind | 5 | 2019-07-15 16:00 | 2007-04-03 10:00 | 2010-08-31 06:00
P0851 TransCanada Keystone KXL Pumpstation #2-Eyre | 2 | Connection | 37-Provost | 0 | 25 | Load | 5 | 2020-11-01 | 2008-08-22 | 2010-08-31 06:00
P0851 TransCanada Keystone KXL Pumpstation #2-Eyre | 1 | Connection | 37-Provost | 0 | 0 | Load | 5 | 2020-11-01 | 2008-08-22 | 2010-08-31 06:00
P0863 TransCanada Keystone KXL Pumpstation #3-Current | 1 | Connection | 42-Hanna | 0 | 25 | Load | 5 | 2020-11-01 | 2008-10-08 | 2010-08-31 06:00
P0864 TransCanada Keystone KXL Pumpstation #4-Armitage | 1 | Connection | 42-Hanna | 0 | 25 | Load | 5 | 2020-11-01 | 2008-10-08 | 2010-08-31 06:00
P0865 TransCanada Keystone KXL Pumpstation #5-Cavendish | 1 | Connection | 48-Empress | 0 | 25 | Load | 5 | 2020-11-01 | 2008-10-08 | 2010-08-31 06:00
P1080 Old Elm Wind Farm | 1 | Connection | 55-Glenwood | 60 | 0 | Wind | 3 | 2019-10-31 16:00 | 2010-04-29 | 2011-06-02 06:00
P0937 Irma Wind Power | 1 | Connection | 32-Wainwright | 90 | 3 | Wind | 4 | 2019-07-01 16:00 | 2009-06-11 | 2011-06-30 06:00
P1258 Fortis Alberta Grist Lake (Pike) Substation | 1 | Connection | 25-Fort McMurray | 0 | 23.2 | Load | 5 | 2020-07-01 16:00 | 2011-08-30 10:00 | 2012-08-17 06:00
P1290 Whitetail Peaking Station | 1 | Connection | 19-Peace River | 0 | 1 | Gas | 5 | 2019-07-30 16:00 | 2011-12-07 | 2013-01-31 17:10
P1290 Whitetail Peaking Station | 2 | Connection | 19-Peace River | 200 | 0 | Gas | 5 | 2019-10-25 16:00 | 2011-12-07 | 2013-01-31 17:10
P0803 Mustus Energy Biomass Generator | 1 | Connection | 18-High Level | 41.5 | 0 | Biomass | 5 | 2019-09-30 16:00 | 2011-11-09 | 2013-05-09 16:43
P1250 E.ON Grizzly Bear Wind | 1 | Connection | 13-Lloydminster | 120 | 1.5 | Wind | 5 | 2020-12-15 16:00 | 2011-08-02 10:00 | 2013-06-21 19:29
P1336 BowArk Energy Queenstown Power Plant | 1 | Connection | 45-Strathmore/Blackie | 94 | 1.7 | Gas Turbine | 5 | 2020-10-01 16:00 | 2012-05-16 10:00 | 2013-06-26 06:00
P1321 Three Creeks Power Plant | 1 | Connection | 19-Peace River | 675 | 10 | Cogen | 5 | 2021-06-30 16:00 | 2012-03-26 | 2013-07-15 17:14
P1289 Maxim Power Deerland Peaking Station | 1 | Connection | 33-Fort Saskatchewan | 185.8 | 0 | Gas Turbine | 5 | 2020-12-01 16:00 | 2011-12-02 | 2013-08-23 06:00
P1404 Cenovus Narrows Lake Substation (Boreal) | 1 | Connection | 25-Fort McMurray | 0 | 35 | Load | 5 | 2020-09-30 16:00 | 2013-01-17 10:00 | 2013-09-20 06:00
P1410 ATCO Heartland Pump Station Connection | 2 | Connection | 56-Vegreville | 0 | 20 | Load | 5 | 2020-11-01 | 2013-02-05 10:00 | 2014-01-09 07:00
P1412 Trans Mountain Pipeline Gainford Substation 16501S | 1 | Connection | 40-Wabamun | 0 | 11 | Load | 5 | 2020-11-01 16:00 | 2013-02-11 10:00 | 2014-03-03 20:30
P1421 ATCO Power Heartland Generating Station | 1 | Connection | 33-Fort Saskatchewan | 510 | 15 | Combined Cycle | 5 | 2019-11-01 16:00 | 2013-03-11 10:00 | 2014-05-26 06:00
P1442 Fortis New Anthony Henday Substation | 1 | Connection | 60-Edmonton | 0 | 21 | Load | 5 | 2020-11-01 16:00 | 2013-05-02 10:00 | 2014-05-26 06:00
P1460 Fortis New Hornbeck Substation | 1 | Connection | 29-Hinton/Edson | 0 | 18 | Load | 5 | 2020-11-01 16:00 | 2013-07-22 10:00 | 2014-05-27 06:00
P1500 Renewable Energy Service WAGF | 1 | Connection | 53-Fort Macleod | 47 | 1 | Wind | 4 | 2020-12-31 16:00 | 2013-11-18 10:00 | 2014-08-28 06:00
P1440 CP Genesee Generating Units 4 & 5 | 1 | Connection | 60-Edmonton | 0 | 50 | Combined Cycle | 5 | 2021-02-01 16:00 | 2013-04-30 10:00 | 2014-11-25 07:00
P1440 CP Genesee Generating Units 4 & 5 | 2 | Connection | 60-Edmonton | 505 | 0 | Combined Cycle | 5 | 2022-03-31 16:00 | 2013-04-30 10:00 | 2014-11-25 07:00
P1440 CP Genesee Generating Units 4 & 5 | 3 | Connection | 60-Edmonton | 505 | 0 | Combined Cycle | 5 | 2023-03-31 16:00 | 2013-04-30 10:00 | 2014-11-25 07:00
P1516 Enbridge Sunken Lake 221S Transformer Change | 1 | BTF | 37-Provost | 0 | 14 | Load | 5 | 2019-05-01 10:00 | 2014-01-23 10:00 | 2014-12-17 07:00
P1505 ATCO City of Grande Prairie New POD | 1 | Connection | 20-Grande Prairie | 0 | 15.5 | Load | 5 | 2021-06-01 16:00 | 2013-12-10 10:00 | 2014-12-19 07:00
P1533 Joss MPC WAGF | 1 | Connection | 48-Empress | 120 | 0 | Wind | 5 | 2019-06-30 16:00 | 2014-03-01 | 2015-01-29 07:00
P1601 ENMAX No 31 Substation 13KV Breakers Addition | 1 | Connection | 6-Calgary | 0 | 0 | Load | 5 | 2019-02-25 16:00 | 2014-09-23 10:00 | 2015-02-02 07:00
P1558 Enbridge New Hardisty Substation | 2 | Connection | 32-Wainwright | 0 | 0 | Load | 5 | 2019-04-09 16:00 | 2014-05-22 | 2015-04-15 06:00
P1567 EDPR Sharp Hills Wind Farm | 1 | Connection | 42-Hanna | 248.4 | 1 | Wind | 5 | 2020-06-01 16:00 | 2014-06-04 | 2015-09-09 06:00
P1567 EDPR Sharp Hills Wind Farm | 2 | Connection | 42-Hanna | 51.6 | 0 | Wind | 5 | 2020-06-01 16:00 | 2014-06-04 | 2015-09-09 06:00
P1566 Calgary Energy Centre Peaking Plant New Generator Capacity | 1 | Connection | 6-Calgary | 150 | 1 | Simple Cycle | 5 | 2021-12-01 16:00 | 2014-06-03 | 2015-09-29 06:00
P1603 ATCO Jasper Interconnection Project Capacity Increase | 1 | Connection | 29-Hinton/Edson | 0 | 3.8 | Load | 5 | 2019-06-01 | 2014-10-10 10:00 | 2015-10-28 06:00
P1649 EPCOR Garneau Area Upgrade | 1 | Connection | 60-Edmonton | 0 | 0 | Load | 4 | 2020-06-30 16:00 | 2015-02-20 10:00 | 2016-02-01 07:00
P1649 EPCOR Garneau Area Upgrade | 2 | Connection | 60-Edmonton | 0 | 20.9 | Load | 4 | 2022-09-30 16:00 | 2015-02-20 10:00 | 2016-02-01 07:00
P1659 EPCOR Strathcona Capacity Increase | 1 | Connection | 60-Edmonton | 0 | 14.2 | Load | 5 | 2019-10-01 16:00 | 2015-03-19 10:00 | 2016-05-17 06:00
P1658 ATCO Ksituan River 754S Capacity Increase | 1 | Connection | 20-Grande Prairie | 0 | 11.7 | Load | 6 | 2019-04-01 16:00 | 2015-03-17 10:00 | 2016-05-31 19:47
P1695 EPCOR Riverview Substation New POD | 1 | Connection | 60-Edmonton | 0 | 24 | Load | 4 | 2019-10-01 16:00 | 2015-08-24 10:00 | 2016-06-29 15:15
P1647 Fengate Strathcona Cogeneration | 1 | Connection | 33-Fort Saskatchewan | 0 | 65 | Cogen | 5 | 2020-03-01 | 2015-02-13 10:00 | 2016-09-09 06:00
P1647 Fengate Strathcona Cogeneration | 2 | Connection | 33-Fort Saskatchewan | 60 | 0 | Cogen | 5 | 2020-10-01 16:00 | 2015-02-13 10:00 | 2016-09-09 06:00
P1704 Paintearth Wind Power | 1 | Connection | 42-Hanna | 150 | 1 | Wind | 4 | 2019-07-01 16:00 | 2015-10-08 10:00 | 2016-10-05 06:00
P1782 Fortis Provost Reliability | 1 | Connection | 37-Provost | 0 | 0 | Load | 5 | 2020-05-01 16:00 | 2016-04-11 10:00 | 2016-10-07 06:00
P1710 Capital Power Halkirk 2 Wind | 1 | Connection | 36-Alliance/Battle River | 150 | 1.8 | Wind | 3 | 2020-12-01 16:00 | 2015-10-22 10:00 | 2016-10-20 06:00
P1728 RESL McLaughlin Phase 2 BTF | 1 | BTF | 53-Fort Macleod | 40 | 0 | Solar | 3 | 2019-09-30 16:00 | 2016-01-05 10:00 | 2016-10-25 06:00
P1734 Suncor Forty Mile Maleb WAGF | 1 | Connection | 4-Medicine Hat | 200 | 0.3 | Wind | 4 | 2020-09-01 10:00 | 2016-01-06 10:00 | 2016-11-01 06:00
P1698 Joss Jenner WAGF - Phase 2 | 1 | BTF | 48-Empress | 180 | 0 | Wind | 5 | 2019-05-01 16:00 | 2015-09-08 10:00 | 2016-11-02 06:00
P1787 ENMAX No.7 Substation 138/25KV Transformer Upgrade | 3 | Connection | 6-Calgary | 0 | 0 | Load | 6 | 2019-04-01 16:00 | 2016-04-18 10:00 | 2016-12-01 07:00
P1718 Wheatland WAGF Project | 1 | Connection | 43-Sheerness | 120 | 0 | Wind | 5 | 2019-12-31 16:00 | 2015-10-30 | 2016-12-16 07:00
P1719 Stirling WAGF Project | 1 | Connection | 54-Lethbridge | 113 | 0 | Wind | 4 | 2019-12-20 16:00 | 2015-10-30 | 2016-12-16 07:00
P1826 Fortis GP Joule Canada Cluny DG | 1 | BTF | 45-Strathmore/Blackie | 1.2 | 0 | Solar | 3 | 2019-10-31 16:00 | 2016-07-29 10:00 | 2017-01-18 07:00
P1812 Suncor Forty Mile Granlea WAGF | 1 | Connection | 4-Medicine Hat | 200 | 0.3 | Wind | 4 | 2020-06-01 10:00 | 2016-07-04 10:00 | 2017-02-28 07:00
P1756 TPG Canyon Creek PHES Storage Project | 1 | Connection | 29-Hinton/Edson | 75 | 64 | Pumped Storage | 3 | 2021-08-10 16:00 | 2016-03-02 10:00 | 2017-03-23 06:00
P1849 Fortis Burdett 368S DG P/V | 1 | BTF | 52-Vauxhall | 9.5 | 0 | Solar | 5 | 2019-10-30 16:00 | 2016-08-24 10:00 | 2017-03-24 06:00
P1837 Fortis 498S Tilley DG PV | 1 | BTF | 52-Vauxhall | 14 | 0 | Solar | 5 | 2019-06-03 16:00 | 2016-08-05 10:00 | 2017-03-31 06:00
P1838 Fortis 895S Suffield DG PV | 1 | BTF | 4-Medicine Hat | 23 | 0 | Solar | 5 | 2019-10-03 16:00 | 2016-08-05 10:00 | 2017-03-31 06:00
P1831 Fortis 255S Vulcan Faribault Farms DG PV | 1 | BTF | 49-Stavely | 14 | 0 | Solar | 3 | 2020-08-01 16:00 | 2016-08-05 10:00 | 2017-04-21 18:47
P1851 Fortis Monarch 492S DER Solar | 1 | BTF | 54-Lethbridge | 20 | 0 | Solar | 3 | 2020-08-01 16:00 | 2016-08-26 10:00 | 2017-04-21 18:49
P1870 Fortis Stavely 349S DER Solar | 1 | BTF | 49-Stavely | 8.5 | 0 | Solar | 3 | 2020-08-01 16:00 | 2016-10-05 10:00 | 2017-04-21 18:50
P1833 Fortis Tilley 498S DG Gas | 1 | BTF | 47-Brooks | 16 | 0 | Gas | 3 | 2019-11-15 16:00 | 2016-08-05 10:00 | 2017-05-12 06:00
P1800 Capital Power Whitla Wind Power Facility | 1 | Connection | 4-Medicine Hat | 201.6 | 3.5 | Wind | 5 | 2019-09-01 | 2016-05-25 10:00 | 2017-05-18 06:00
P1800 Capital Power Whitla Wind Power Facility | 2 | Connection | 4-Medicine Hat | 97.2 | 1 | Wind | 5 | 2020-09-01 16:00 | 2016-05-25 10:00 | 2017-05-18 06:00
P1898 Pattern Lanfine North Wind | 1 | Connection | 42-Hanna | 145 | 0 | Wind | 3 | 2020-05-01 16:00 | 2016-12-02 10:00 | 2017-06-16 06:00
P1877 Sunset Solar Project | 1 | Connection | 52-Vauxhall | 60 | 0.3 | Solar | 3 | 2020-06-30 16:00 | 2016-10-20 10:00 | 2017-06-27 06:00
P1850 Fortis Coaldale 254S DER Solar 3 | 1 | BTF | 54-Lethbridge | 22 | 0 | Solar | 3 | 2020-08-01 16:00 | 2016-08-26 10:00 | 2017-07-20 21:22
P1862 Fortis Spring Coulee 385S Solar DG | 1 | BTF | 55-Glenwood | 28.5 | 0 | Solar | 5 | 2019-08-22 16:00 | 2016-09-28 10:00 | 2017-07-28 18:13
P1879 Claresholm Solar Connection | 1 | Connection | 49-Stavely | 130 | 0.6 | Solar | 3 | 2020-06-30 16:00 | 2016-10-25 10:00 | 2017-08-03 06:00
P1839 Fortis 421S Hays DG PV | 1 | BTF | 52-Vauxhall | 15 | 0 | Solar | 5 | 2019-10-14 16:00 | 2016-08-05 10:00 | 2017-08-11 06:00
P1842 Fortis 158S Vauxhall DG PV | 1 | BTF | 52-Vauxhall | 11 | 0 | Solar | 3 | 2019-06-03 16:00 | 2016-08-05 10:00 | 2017-08-11 06:00
P1869 Fortis Enchant 447S DER Solar | 1 | BTF | 52-Vauxhall | 68.2 | 0 | Solar | 5 | 2019-10-28 16:00 | 2016-10-03 10:00 | 2017-08-11 06:00
P1878 Fortis Krafte 257S Hull DER Solar | 1 | BTF | 52-Vauxhall | 24.5 | 0 | Solar | 5 | 2019-10-15 16:00 | 2016-10-24 10:00 | 2017-08-11 06:00
P1902 FortisAlberta Fincastle Area Capacity and Reliability Project | 1 | Connection | 52-Vauxhall | 0 | 11.1 | Load | 5 | 2019-06-01 16:00 | 2016-12-20 10:00 | 2017-08-31 22:00
P1864 BowArk Drywood Gas Generator | 1 | Connection | 45-Strathmore/Blackie | 38 | 1 | Gas | 3 | 2020-10-01 10:00 | 2016-09-30 10:00 | 2017-09-08 22:00
P1766 FortisAlberta Warner-Conrad Area Upgrade | 1 | Connection | 55-Glenwood | 0 | 3.5 | Load | 5 | 2019-06-14 16:00 | 2016-03-09 10:00 | 2017-09-26 06:00
P1904 FortisAlberta Crossfield Area Capacity and Reliability Project | 1 | Connection | 57-Airdrie | 0 | 4.9 | Load | 5 | 2019-11-01 16:00 | 2016-12-20 10:00 | 2017-09-28 06:00
P1908 TransAlta Cowley Ridge 1 Wind | 1 | BTF | 53-Fort Macleod | 21 | 0.5 | Wind | 5 | 2019-12-31 16:00 | 2016-12-22 10:00 | 2017-10-04 22:00
P1917 FortisAlberta West Brooks DER Solar | 1 | BTF | 47-Brooks | 19.2 | 0 | Solar | 5 | 2019-10-15 10:00 | 2017-02-06 10:00 | 2017-10-17 06:00
P1907 FortisAlberta Vulcan-Stavely Area Capacity and Reliability | 1 | Connection | 49-Stavely | 0 | 3.5 | Load | 5 | 2019-11-01 16:00 | 2017-01-18 10:00 | 2017-10-19 22:00
P1982 EDTI DG Solar BTF | 1 | BTF | 60-Edmonton | 0 | 0 | Solar | 3 | 2019-11-30 | 2017-07-07 10:00 | 2017-10-24 06:00
P1932 FortisAlberta Namaka DER Solar | 1 | BTF | 45-Strathmore/Blackie | 15.5 | 0 | Solar | 3 | 2019-06-28 16:00 | 2017-04-10 10:00 | 2017-10-25 06:00
P1964 FortisAlberta Killarney Lake DER Solar | 1 | BTF | 37-Provost | 0 | 0 | Solar | 3 | 2019-01-01 16:00 | 2017-05-22 10:00 | 2017-11-24 07:00
P1922 FortisAlberta Vauxhall Solar DER | 1 | BTF | 52-Vauxhall | 22 | 0 | Solar | 5 | 2019-09-30 16:00 | 2017-03-14 10:00 | 2017-12-06 22:40
P1909 TransAlta Garden Plain Wind | 1 | Connection | 42-Hanna | 130 | 4 | Wind | 3 | 2020-06-14 | 2016-12-22 10:00 | 2017-12-07 07:00
P1853 Fortis Buffalo Atlee Cluster 1 WAGF | 1 | BTF | 48-Empress | 18.3 | 0 | Wind | 5 | 2020-12-01 16:00 | 2016-08-30 10:00 | 2017-12-07 18:13
P1892 Fortis Buffalo Atlee Cluster 3 WAGF DER | 1 | BTF | 48-Empress | 17.3 | 0 | Wind | 5 | 2020-12-01 16:00 | 2016-11-15 10:00 | 2017-12-07 18:16
P1923 CNRL Kirby North Load | 1 | Connection | 25-Fort McMurray | 0 | 29 | Load | 6 | 2019-04-01 16:00 | 2017-03-21 10:00 | 2017-12-08 23:33
P1852 Fortis Stirling 67S DG P/V | 1 | BTF | 55-Glenwood | 17.4 | 0 | Solar | 5 | 2019-08-05 16:00 | 2016-08-30 10:00 | 2017-12-21 17:34
P2021 Suncor TG1 & TG2 Testing and Commissioning | 1 | BTF | 25-Fort McMurray | 0 | 0 | Equipment Change | 6 | 2019-07-28 | 2017-11-27 10:00 | 2018-02-07 23:17
P1984 FortisAlberta Gleichen DG Solar | 1 | BTF | 45-Strathmore/Blackie | 17 | 0 | Solar | 3 | 2019-06-28 16:00 | 2017-07-17 10:00 | 2018-02-14 07:00
P1840 Fortis 275S Jenner Solar DER | 1 | BTF | 48-Empress | 23 | 0 | Solar | 5 | 2020-11-12 16:00 | 2016-08-05 10:00 | 2018-03-09 23:03
P1918 FortisAlberta Conrad DER Solar 1 | 1 | BTF | 52-Vauxhall | 18.4 | 0 | Solar | 3 | 2019-07-15 16:00 | 2017-02-06 10:00 | 2018-03-16 06:00
P1959 FortisAlberta Conrad DER Solar 2 | 1 | BTF | 52-Vauxhall | 22.5 | 0 | Solar | 3 | 2019-11-29 16:00 | 2017-05-08 10:00 | 2018-03-16 06:00
P1967 FortisAlberta Jenner 275S DER | 1 | BTF | 48-Empress | 16.1 | 0 | Gas Turbine | 5 | 2019-07-15 16:00 | 2017-06-06 10:00 | 2018-03-27 06:00
P2012 Keyera West Pembina 359S Gas Turbine | 1 | BTF | 30-Drayton Valley | 4.9 | 0 | Gas Turbine | 5 | 2019-11-01 16:00 | 2017-10-25 10:00 | 2018-04-20 21:43
P1927 Solar Krafte Brooks | 1 | Connection | 47-Brooks | 400 | 1 | Solar | 3 | 2020-04-01 16:00 | 2017-03-23 10:00 | 2018-05-03 17:10
P1962 FortisAlberta Provost DER Solar | 1 | BTF | 37-Provost | 0 | 0 | Solar | 3 | 2019-01-01 16:00 | 2017-05-10 10:00 | 2018-05-09 14:16
P1961 FortisAlberta Wainwright DER Solar | 1 | BTF | 32-Wainwright | 0 | 0 | Solar | 3 | 2019-01-01 16:00 | 2017-05-10 10:00 | 2018-05-09 14:17
P2023 FortisAlberta Kananaskis Area Reliability | 1 | Connection | 44-Seebe | 0 | 4.7 | Load | 5 | 2019-11-01 16:00 | 2017-11-22 10:00 | 2018-05-14 22:00
P2035 FortisAlberta Willesdengreen DER Gas Turbine | 1 | BTF | 30-Drayton Valley | 5 | 0 | Gas Turbine | 3 | 2019-09-01 16:00 | 2018-01-02 10:00 | 2018-05-28 18:57
P1865 Fortis Warner 344S DER Solar | 1 | BTF | 55-Glenwood | 6 | 0 | Solar | 5 | 2019-05-15 16:00 | 2016-10-03 10:00 | 2018-06-22 06:00
P1976 FortisAlberta Brooks DER Solar | 1 | BTF | 47-Brooks | 13.7 | 0 | Solar | 5 | 2019-08-05 16:00 | 2017-06-20 10:00 | 2018-07-09 06:00
P1934 FortisAlberta Empress DER Solar | 1 | BTF | 48-Empress | 20.5 | 0 | Solar | 3 | 2019-05-01 16:00 | 2017-04-12 10:00 | 2018-08-22 16:37
P1960 FortisAlberta Bassano DER Solar | 1 | BTF | 47-Brooks | 0 | 0 | Solar | 3 | 2019-12-31 16:00 | 2017-05-10 10:00 | 2018-08-24 15:24
P2106 COMH Medicine Hat Area Upgrade | 1 | BTF | 4-Medicine Hat | 0 | 0 | Equipment Change | 5 | 2019-11-01 16:00 | 2018-06-25 10:00 | 2018-09-14 06:00
P2009 Greengate Travers MPC Solar | 1 | Connection | 49-Stavely | 400 | 0.5 | Solar | 3 | 2020-12-01 16:00 | 2017-10-20 10:00 | 2018-09-18 06:00
P2028 FortisAlberta Barrhead-Westlock Area Reliability | 1 | Connection | 40-Wabamun | 0 | 0 | Load | 3 | 2020-12-01 16:00 | 2017-12-05 10:00 | 2018-09-21 06:00
P2161 TransAlta Sundance 2 | 1 | BTF | 40-Wabamun | -280 | 0 | Coal | 5 | 2019-04-26 16:00 | 2018-09-28 10:00 | 2018-10-25 21:15
P2038 FortisAlberta Empress 394S DER Solar | 1 | BTF | 48-Empress | 15.6 | 0 | Solar | 3 | 2019-05-01 16:00 | 2018-01-08 10:00 | 2018-11-06 07:00
P2057 Imperial Oil Edmonton 95S Cogen | 1 | BTF | 60-Edmonton | 0 | 0 | Cogen | 5 | 2019-11-01 16:00 | 2018-02-15 10:00 | 2018-11-13 16:01
P2142 Whitecourt Generation Station Change | 1 | BTF | 26-Swan Hills | 0 | 0 | Equipment Change | 5 | 2019-05-03 16:00 | 2018-08-21 10:00 | 2018-11-13 16:38
P1926 Solar Krafte Vauxhall | 1 | Connection | 52-Vauxhall | 150 | 0.4 | Solar | 3 | 2020-04-01 16:00 | 2017-03-23 10:00 | 2018-11-29 18:44
P2151 COMH Central Area Upgrade | 1 | BTF | 4-Medicine Hat | 0 | 0 | Other | 5 | 2019-11-01 16:00 | 2018-09-07 10:00 | 2018-12-10 15:32
P2108 FortisAlberta Entwistle 235S DER Gas | 1 | BTF | 40-Wabamun | 1.8 | 0 | Gas Turbine | 4 | 2019-06-03 16:00 | 2018-06-19 10:00 | 2018-12-21 07:00
P2174 ATCO Freeman Lake 742S Contract Change (POD Salvage) | 1 | Contract | 26-Swan Hills | 0 | -3.1 | DTS | 5 | 2019-05-16 16:00 | 2018-10-25 10:00 | 2019-02-05 07:00
P2030 FortisAlberta Strathmore 151S DER Solar 2 | 1 | BTF | 45-Strathmore/Blackie | 19.5 | 0 | Solar | 3 | 2019-11-15 16:00 | 2017-12-07 10:00 | 2019-02-11 20:52
P2029 FortisAlberta Strathmore 151S DER Solar 1 | 1 | BTF | 45-Strathmore/Blackie | 16.7 | 0 | Solar | 3 | 2019-11-15 16:00 | 2017-12-06 10:00 | 2019-02-11 20:53
P2010 FortisAlberta Coaldale 254S DER Cogen | 1 | BTF | 54-Lethbridge | 6 | 0 | Cogen | 5 | 2019-08-01 16:00 | 2017-10-23 10:00 | 2019-02-12 23:18
P2125 Capital Power Genesee Unit 1 Change | 1 | BTF | 40-Wabamun | 0 | 0 | Equipment Change | 5 | 2019-05-17 16:00 | 2018-07-12 10:00 | 2019-02-14 05:10
P2184 EDTI Victoria Change | 1 | Connection | 60-Edmonton | 0 | 0 | Equipment Change | 4 | 2019-12-15 | 2018-11-21 09:00 | 2019-02-22 07:00
P2197 FortisAlberta East Edmonton 38S Change | 1 | Connection | 60-Edmonton | 0 | 0 | Other | 4 | 2019-08-16 16:00 | 2019-01-11 10:00 | 2019-02-27 07:00
P2095 Syncrude Mildred Lake Change | 1 | BTF | 25-Fort McMurray | 0 | 0 | Cogen | 5 | 2019-07-22 16:00 | 2018-05-23 10:00 | 2019-02-28 07:00
P1778 ATCO Aspen SAGD Project - DTS | 1 | Connection | 25-Fort McMurray | 0 | 40 | Load | 3 | 2021-03-29 16:00 | 2016-04-04 10:00 | 2019-03-01 00:06
P1779 Imperial Oil Aspen SAGD Project - STS | 1 | Connection | 25-Fort McMurray | 30 | 0 | Cogen | 3 | 2021-03-29 16:00 | 2016-04-04 10:00 | 2019-03-01 00:06
P2123 FortisAlberta Lethbridge Area Reliability | 1 | Connection | 54-Lethbridge | 0 | 0 | Other | 3 | 2020-07-01 16:00 | 2018-07-11 10:00 | 2019-03-01 23:40
P2050 Enbridge Abee 993S Upgrade | 1 | Connection | 27-Athabasca/Lac La Biche | 0 | 13 | Load | 3 | 2021-12-01 16:00 | 2018-02-05 10:00 | 2019-03-04 23:00
P2181 ATCO Bridge Creek 798S Contract Change | 1 | Contract | 20-Grande Prairie | 0 | -5 | DTS | 5 | 2019-08-01 16:00 | 2018-11-16 09:00 | 2019-03-05 07:00
P2082 Suncor Base Plant Cogen | 1 | Connection | 25-Fort McMurray | 815 | 0 | Cogen | 3 | 2021-07-01 16:00 | 2018-04-24 10:00 | 2019-03-19 15:49
P2079 FortisAlberta Blackfalds 198S DER Gas | 1 | BTF | 35-Red Deer | 4.5 | 0 | Gas Turbine | 4 | 2019-07-01 16:00 | 2018-04-11 10:00 | 2019-03-28 06:00
P2079 FortisAlberta Blackfalds 198S DER Gas | 2 | BTF | 35-Red Deer | 4 | 0 | Gas Turbine | 4 | 2020-07-01 16:00 | 2018-04-11 10:00 | 2019-03-28 06:00
BTF denotes a behind the fence project and is not governed by the Connection Process. DTS and STS project types denote active contract change requests and are not governed by the Connection Process.