## AESO Connection Pro - Data List
Project | Subproject | Project Type | Planning Area | STS MW Change | DTS MW Change | MW Type | Process Stage | Planned ISD | Applied On | Entered Queue
P0513 Pteragen Peace Butte Wind Farm | 1 | Connection | 04-Medicine Hat | 119.7 | 0.1 | Wind | 5 | 2022-12-01 16:00 | 2005-10-14 | 2010-08-31 06:00
P0479 Naturener Wild Rose 1 Wind Farm | 1 | Connection | 04-Medicine Hat | 217.6 | 4 | Wind | 5 | 2022-08-15 16:00 | 2005-05-12 | 2010-08-31 06:00
P0693 Naturener Wild Rose 2 Wind Farm | 1 | Connection | 04-Medicine Hat | 192 | 4 | Wind | 5 | 2022-08-15 16:00 | 2007-04-03 10:00 | 2010-08-31 06:00
P0851 TransCanada Keystone KXL Pumpstation #2-Eyre | 2 | Connection | 37-Provost | 0 | 25 | Load | 5 | 2020-11-01 | 2008-08-22 | 2010-08-31 06:00
P0851 TransCanada Keystone KXL Pumpstation #2-Eyre | 1 | Connection | 37-Provost | 0 | 0 | Load | 5 | 2020-11-01 | 2008-08-22 | 2010-08-31 06:00
P0863 TransCanada Keystone KXL Pumpstation #3-Current | 1 | Connection | 42-Hanna | 0 | 25 | Load | 5 | 2020-11-01 | 2008-10-08 | 2010-08-31 06:00
P0864 TransCanada Keystone KXL Pumpstation #4-Armitage | 1 | Connection | 42-Hanna | 0 | 22 | Load | 5 | 2020-11-01 | 2008-10-08 | 2010-08-31 06:00
P0865 TransCanada Keystone KXL Pumpstation #5-Cavendish | 1 | Connection | 48-Empress | 0 | 25 | Load | 5 | 2020-11-01 | 2008-10-08 | 2010-08-31 06:00
P1080 Old Elm Wind Farm | 1 | Connection | 55-Glenwood | 60 | 0 | Wind | 3 | 2022-10-31 16:00 | 2010-04-29 | 2011-06-02 06:00
P1290 Whitetail Peaking Station | 1 | Connection | 19-Peace River | 0 | 1 | Gas | 5 | 2023-05-22 16:00 | 2011-12-07 | 2013-01-31 17:10
P1290 Whitetail Peaking Station | 2 | Connection | 19-Peace River | 200 | 0 | Gas | 5 | 2023-05-22 16:00 | 2011-12-07 | 2013-01-31 17:10
P1250 Enel Grizzly Bear Wind | 1 | Connection | 13-Lloydminster | 120 | 1.5 | Wind | 5 | 2021-10-01 16:00 | 2011-08-02 10:00 | 2013-06-21 19:29
P1289 Maxim Power Deerland Peaking Station | 1 | Connection | 33-Fort Saskatchewan | 185.8 | 0 | Gas Turbine | 5 | 2020-12-01 16:00 | 2011-12-02 | 2013-08-23 06:00
P1410 ATCO Heartland Pump Station Connection | 2 | Connection | 56-Vegreville | 0 | 20 | Load | 5 | 2020-11-01 | 2013-02-05 10:00 | 2014-01-09 07:00
P1412 Trans Mountain Pipeline Gainford Substation 16501S | 1 | Connection | 40-Wabamun | 0 | 11 | Load | 5 | 2022-06-01 16:00 | 2013-02-11 10:00 | 2014-03-03 20:30
P1442 Fortis New Anthony Henday Substation | 1 | Connection | 60-Edmonton | 0 | 21 | Load | 5 | 2022-06-01 16:00 | 2013-05-02 10:00 | 2014-05-26 06:00
P1460 Fortis New Hornbeck Substation | 1 | Connection | 29-Hinton/Edson | 0 | 18 | Load | 5 | 2022-06-01 16:00 | 2013-07-22 10:00 | 2014-05-27 06:00
P1500 Renewable Energy Service WAGF | 1 | Connection | 53-Fort Macleod | 47 | 1 | Wind | 5 | 2022-11-30 16:00 | 2013-11-18 10:00 | 2014-08-28 06:00
P1505 ATCO City of Grande Prairie New POD | 1 | Connection | 20-Grande Prairie | 0 | 15.5 | Load | 5 | 2021-12-01 16:00 | 2013-12-10 10:00 | 2014-12-19 07:00
P1533 Joss MPC WAGF | 1 | Connection | 48-Empress | 122.4 | 0 | Wind | 5 | 2021-05-31 16:00 | 2014-03-01 | 2015-01-29 07:00
P1567 EDPR Sharp Hills Wind Farm | 1 | Connection | 42-Hanna | 248.4 | 1 | Wind | 5 | 2020-11-15 | 2014-06-04 | 2015-09-09 06:00
P1567 EDPR Sharp Hills Wind Farm | 2 | Connection | 42-Hanna | 51.6 | 0 | Wind | 5 | 2020-11-15 | 2014-06-04 | 2015-09-09 06:00
P1649 EPCOR Garneau Area Upgrade | 1 | Connection | 60-Edmonton | 0 | 0 | Load | 4 | 2021-10-31 | 2015-02-20 10:00 | 2016-02-01 07:00
P1649 EPCOR Garneau Area Upgrade | 2 | Connection | 60-Edmonton | 0 | 20.9 | Load | 4 | 2023-10-31 16:00 | 2015-02-20 10:00 | 2016-02-01 07:00
P1659 EPCOR Strathcona Capacity Increase | 1 | Connection | 60-Edmonton | 0 | 14.2 | Load | 5 | 2020-09-01 16:00 | 2015-03-19 10:00 | 2016-05-17 06:00
P1647 Fengate Strathcona Cogeneration | 2 | Connection | 33-Fort Saskatchewan | 60 | 0 | Cogen | 5 | 2020-10-01 16:00 | 2015-02-13 10:00 | 2016-09-09 06:00
P1647 Fengate Strathcona Cogeneration | 1 | Connection | 33-Fort Saskatchewan | 0 | 65 | Cogen | 5 | 2021-02-01 16:00 | 2015-02-13 10:00 | 2016-09-09 06:00
P1704 Paintearth Wind Power | 1 | Connection | 42-Hanna | 150 | 1 | Wind | 4 | 2021-09-30 16:00 | 2015-10-08 10:00 | 2016-10-05 06:00
P1782 Fortis Provost Reliability | 1 | Connection | 37-Provost | 0 | 0 | Load | 5 | 2021-05-01 | 2016-04-11 10:00 | 2016-10-07 06:00
P1734 Suncor Forty Mile Maleb WAGF | 1 | Connection | 04-Medicine Hat | 200 | 0.3 | Wind | 5 | 2022-09-01 10:00 | 2016-01-06 10:00 | 2016-11-01 06:00
P1698 Joss Jenner WAGF - Phase 2 | 1 | BTF | 48-Empress | 71.4 | 0 | Wind | 5 | 2021-05-31 16:00 | 2015-09-08 10:00 | 2016-11-02 06:00
P1718 Wheatland WAGF Project | 1 | Connection | 43-Sheerness | 120 | 0 | Wind | 5 | 2022-09-30 16:00 | 2015-10-30 | 2016-12-16 07:00
P1719 Stirling WAGF Project | 1 | Connection | 54-Lethbridge | 113 | 0 | Wind | 5 | 2021-05-31 16:00 | 2015-10-30 | 2016-12-16 07:00
P1812 Suncor Forty Mile Granlea WAGF | 1 | Connection | 04-Medicine Hat | 200 | 0.3 | Wind | 5 | 2021-11-16 16:00 | 2016-07-04 10:00 | 2017-02-28 07:00
P1756 TPG Canyon Creek PHES Storage Project | 1 | Connection | 29-Hinton/Edson | 75 | 64 | Pumped Hydro | 3 | 2021-08-10 16:00 | 2016-03-02 10:00 | 2017-03-23 06:00
P1849 Fortis Burdett 368S DG P/V | 1 | BTF | 52-Vauxhall | 10.5 | 0 | Solar | 5 | 2020-12-15 16:00 | 2016-08-24 10:00 | 2017-03-24 06:00
P1837 Fortis 498S Tilley DG PV | 1 | BTF | 52-Vauxhall | 13 | 0 | Solar | 5 | 2020-10-28 16:00 | 2016-08-05 10:00 | 2017-03-31 06:00
P1831 Fortis 255S Vulcan Faribault Farms DG PV | 1 | BTF | 49-Stavely | 17 | 0 | Solar | 5 | 2021-05-31 16:00 | 2016-08-05 10:00 | 2017-04-21 18:47
P1851 Fortis Monarch 492S DER Solar | 1 | BTF | 54-Lethbridge | 20 | 0 | Solar | 5 | 2021-05-31 16:00 | 2016-08-26 10:00 | 2017-04-21 18:49
P1870 Fortis Stavely 349S DER Solar | 1 | BTF | 49-Stavely | 13 | 0 | Solar | 5 | 2021-05-31 16:00 | 2016-10-05 10:00 | 2017-04-21 18:50
P1833 Fortis Tilley 498S DG Gas | 1 | BTF | 47-Brooks | 16 | 0 | Gas | 3 | 2021-07-01 16:00 | 2016-08-05 10:00 | 2017-05-12 06:00
P1800 Capital Power Whitla Wind Power Facility | 2 | Connection | 04-Medicine Hat | 97.2 | 1 | Wind | 5 | 2020-12-01 16:00 | 2016-05-25 10:00 | 2017-05-18 06:00
P1898 Pattern Lanfine North Wind | 1 | Connection | 42-Hanna | 145 | 0 | Wind | 3 | 2022-09-30 16:00 | 2016-12-02 10:00 | 2017-06-16 06:00
P1850 Fortis Coaldale 254S DER Solar 3 | 1 | BTF | 54-Lethbridge | 22 | 0 | Solar | 5 | 2021-05-31 16:00 | 2016-08-26 10:00 | 2017-07-20 21:22
P1862 Fortis Spring Coulee 385S Solar DG | 1 | BTF | 55-Glenwood | 28.5 | 0 | Solar | 5 | 2021-10-15 16:00 | 2016-09-28 10:00 | 2017-07-28 18:13
P1879 Claresholm Solar Connection | 1 | Connection | 49-Stavely | 130 | 0.6 | Solar | 5 | 2020-10-31 16:00 | 2016-10-25 10:00 | 2017-08-03 06:00
P1839 Fortis 421S Hays DG PV | 1 | BTF | 52-Vauxhall | 13.4 | 0 | Solar | 5 | 2020-10-15 16:00 | 2016-08-05 10:00 | 2017-08-11 06:00
P1839 Fortis 421S Hays DG PV | 2 | BTF | 52-Vauxhall | 0 | 0 | Solar | 5 | 2021-03-04 16:00 | 2016-08-05 10:00 | 2017-08-11 06:00
P1902 FortisAlberta Fincastle Area Capacity and Reliability Project | 1 | Connection | 52-Vauxhall | 0 | 11.1 | Load | 5 | 2020-06-30 16:00 | 2016-12-20 10:00 | 2017-08-31 22:00
P1864 BowArk Drywood Gas Generator | 1 | Connection | 45-Strathmore/Blackie | 38 | 1 | Gas | 5 | 2021-01-31 10:00 | 2016-09-30 10:00 | 2017-09-08 22:00
P1982 EDTI DG Solar BTF | 1 | BTF | 60-Edmonton | 0 | 0 | Solar | 3 | 2021-01-31 | 2017-07-07 10:00 | 2017-10-24 06:00
P1932 FortisAlberta Namaka DER Solar | 1 | BTF | 45-Strathmore/Blackie | 15.5 | 0 | Solar | 5 | 2021-04-01 16:00 | 2017-04-10 10:00 | 2017-10-25 06:00
P1909 TransAlta Garden Plain Wind | 1 | Connection | 42-Hanna | 130 | 4 | Wind | 3 | 2021-10-01 16:00 | 2016-12-22 10:00 | 2017-12-07 07:00
P1853 Fortis Buffalo Atlee Cluster 1 WAGF | 1 | BTF | 48-Empress | 18.3 | 0 | Wind | 5 | 2021-12-01 17:00 | 2016-08-30 10:00 | 2017-12-07 18:13
P1892 Fortis Buffalo Atlee Cluster 3 WAGF DER | 1 | BTF | 48-Empress | 17.3 | 0 | Wind | 5 | 2021-12-01 17:00 | 2016-11-15 10:00 | 2017-12-07 18:16
P2021 Suncor TG1 & TG2 Testing and Commissioning | 1 | BTF | 25-Fort McMurray | 0 | 0 | Equipment Change | 6 | 2020-08-10 16:00 | 2017-11-27 10:00 | 2018-02-07 23:17
P1984 FortisAlberta Gleichen DG Solar | 1 | BTF | 45-Strathmore/Blackie | 17 | 0 | Solar | 3 | 2021-10-15 16:00 | 2017-07-17 10:00 | 2018-02-14 07:00
P1840 Fortis 275S Jenner Solar DER | 1 | BTF | 48-Empress | 23 | 0 | Solar | 5 | 2020-11-12 16:00 | 2016-08-05 10:00 | 2018-03-09 23:03
P1918 FortisAlberta Conrad DER Solar 1 | 1 | BTF | 52-Vauxhall | 18.4 | 0 | Solar | 5 | 2021-04-15 16:00 | 2017-02-06 10:00 | 2018-03-16 06:00
P1959 FortisAlberta Conrad DER Solar 2 | 1 | BTF | 52-Vauxhall | 18 | 0 | Solar | 5 | 2021-04-15 16:00 | 2017-05-08 10:00 | 2018-03-16 06:00
P1967 FortisAlberta Jenner 275S DER | 1 | BTF | 48-Empress | 16.1 | 0 | Gas | 5 | 2021-09-30 10:00 | 2017-06-06 10:00 | 2018-03-27 06:00
P2012 Keyera West Pembina 359S Gas Turbine | 1 | BTF | 30-Drayton Valley | 0 | 0 | Gas Turbine | 6 | 2020-07-01 16:00 | 2017-10-25 10:00 | 2018-04-20 21:43
P1927 Solar Krafte Brooks | 1 | Connection | 47-Brooks | 400 | 1 | Solar | 3 | 2022-06-30 16:00 | 2017-03-23 10:00 | 2018-05-03 17:10
P2009 Greengate Travers MPC Solar | 1 | Connection | 49-Stavely | 400 | 0.5 | Solar | 5 | 2020-12-01 16:00 | 2017-10-20 10:00 | 2018-09-18 06:00
P2028 FortisAlberta Barrhead-Westlock Area Reliability | 1 | Connection | 40-Wabamun | 0 | 0 | Load | 3 | 2020-12-01 16:00 | 2017-12-05 10:00 | 2018-09-21 06:00
P2057 Imperial Oil Edmonton 95S Cogen | 2 | BTF | 60-Edmonton | 0 | 0 | Cogen | 5 | 2020-08-24 16:00 | 2018-02-15 10:00 | 2018-11-13 16:01
P1926 Solar Krafte Vauxhall | 1 | Connection | 52-Vauxhall | 150 | 0.4 | Solar | 3 | 2021-12-31 16:00 | 2017-03-23 10:00 | 2018-11-29 18:44
P2151 CMH Central Area Upgrade | 1 | BTF | 04-Medicine Hat | 0 | 0 | Other | 5 | 2020-10-30 16:00 | 2018-09-07 10:00 | 2018-12-10 15:32
P2108 FortisAlberta Entwistle 235S DER Gas | 1 | BTF | 40-Wabamun | 1.8 | 0 | Gas | 3 | 2020-09-01 16:00 | 2018-06-19 10:00 | 2018-12-21 07:00
P2030 FortisAlberta Strathmore 151S DER Solar 2 | 1 | BTF | 45-Strathmore/Blackie | 19.5 | 0 | Solar | 3 | 2021-08-15 16:00 | 2017-12-07 10:00 | 2019-02-11 20:52
P2029 FortisAlberta Strathmore 151S DER Solar 1 | 1 | BTF | 45-Strathmore/Blackie | 16.7 | 0 | Solar | 3 | 2021-08-15 16:00 | 2017-12-06 10:00 | 2019-02-11 20:53
P2123 FortisAlberta Lethbridge Area Reliability | 1 | Connection | 54-Lethbridge | 0 | 0 | Other | 3 | 2021-11-01 16:00 | 2018-07-11 10:00 | 2019-03-01 23:40
P2050 Enbridge Abee 993S Upgrade | 1 | Connection | 27-Athabasca/Lac La Biche | 0 | 13 | Load | 5 | 2021-03-01 16:00 | 2018-02-05 10:00 | 2019-03-04 23:00
P2082 Suncor Base Plant Cogen | 1 | Connection | 25-Fort McMurray | 815 | 0 | Cogen | 3 | 2021-07-01 16:00 | 2018-04-24 10:00 | 2019-03-19 15:49
P2061 ATCO Michichi Creek 802S DER Solar | 1 | BTF | 42-Hanna | 11 | 0 | Solar | 3 | 2020-09-30 16:00 | 2018-02-20 10:00 | 2019-04-09 22:32
P2059 ATCO Three Hills 770S DER Solar 1 | 1 | BTF | 42-Hanna | 14 | 0 | Solar | 3 | 2020-09-30 16:00 | 2018-02-20 10:00 | 2019-04-09 22:32
P2210 EDTI Strathcona Change | 1 | Connection | 60-Edmonton | 0 | 0 | Other | 6 | 2020-10-26 16:00 | 2019-02-19 10:00 | 2019-04-12 18:39
P2034 Cold Lake Area Energy Centre | 1 | Connection | 28-Cold Lake | 100 | 30 | Cogen | 3 | 2020-10-01 16:00 | 2018-01-02 10:00 | 2019-04-23 18:23
P2110 ATCO Power Poplar Hill Gas | 1 | BTF | 20-Grande Prairie | 32 | 0 | Gas Turbine | 5 | 2022-07-01 16:00 | 2018-06-26 10:00 | 2019-05-08 18:45
P2134 CNRL Muskeg River 847S Change | 1 | BTF | 25-Fort McMurray | 0 | 0 | Other | 5 | 2022-06-01 16:00 | 2018-08-07 10:00 | 2019-05-16 16:44
P2217 FortisAlberta Marion 21S Contract Change | 1 | Contract | 40-Wabamun | 0 | -8.6 | DTS | 6 | 2021-10-31 | 2019-03-26 10:00 | 2019-05-21 22:00
P2150 ATCO Power Valleyview Gas | 1 | BTF | 23-Valleyview | 32 | 0 | Gas Turbine | 3 | 2022-07-01 16:00 | 2018-09-07 10:00 | 2019-06-07 22:00
P2032 Cascade Combined Cycle | 1 | Connection | 29-Hinton/Edson | 900 | 11.5 | Combined Cycle | 3 | 2022-03-25 16:00 | 2018-01-02 10:00 | 2019-06-17 14:31
P2041 TransAlta Windrise MPC Wind | 1 | Connection | 53-Fort Macleod | 220 | 3 | Wind | 4 | 2020-12-17 16:00 | 2018-01-12 10:00 | 2019-06-21 06:00
P2122 Cypress Wind Project Connection | 1 | Connection | 04-Medicine Hat | 201.6 | 2.7 | Wind | 4 | 2021-11-01 16:00 | 2018-07-12 10:00 | 2019-06-21 06:00
P2092 FortisAlberta Brooks 121S DER Solar (257LE) | 1 | BTF | 47-Brooks | 12 | 0 | Solar | 5 | 2020-12-31 16:00 | 2018-05-14 10:00 | 2019-07-16 06:00
P2171 FortisAlberta Westfield 107S DER Solar | 1 | BTF | 52-Vauxhall | 18.4 | 9.3 | Solar | 5 | 2020-11-09 16:00 | 2018-10-22 10:00 | 2019-07-18 06:00
P2222 ENMAX Crossfield CRS3 Battery Storage | 1 | BTF | 57-Airdrie | 0 | 0 | Battery | 5 | 2020-10-06 16:00 | 2019-04-08 10:00 | 2019-08-06 19:53
P2224 Capital Power Genesee Unit 2 Change | 1 | BTF | 40-Wabamun | 0 | 0 | Other | 5 | 2021-04-06 16:00 | 2019-04-12 10:00 | 2019-08-12 06:00
P2198 TransAlta Summerview 2 Battery Storage | 1 | BTF | 53-Fort Macleod | 10 | 0 | Battery | 5 | 2020-08-06 16:00 | 2019-01-11 10:00 | 2019-08-14 15:01
P2255 Pembina BFG 452S Contract Change | 1 | Contract | 33-Fort Saskatchewan | 0 | 2.5 | DTS | 3 | 2020-12-01 16:00 | 2019-07-09 10:00 | 2019-08-21 06:00
P2137 Enerfin Winnifred MPC Wind | 1 | Connection | 04-Medicine Hat | 90 | 1 | Wind | 3 | 2021-12-01 16:00 | 2018-08-10 10:00 | 2019-08-26 19:20
P2245 ATCO Freeman Lake 742S Change | 2 | BTF | 26-Swan Hills | 0 | 0 | Other | 5 | 2021-02-01 16:00 | 2019-06-20 10:00 | 2019-09-05 20:08
P2086 FortisAlberta Brooks 121S DER Solar (83L) | 1 | BTF | 47-Brooks | 13 | 0 | Solar | 5 | 2020-12-31 16:00 | 2018-05-14 10:00 | 2019-09-09 06:00
P2180 Heartland Rainbow Lake Gas | 1 | Connection | 17-Rainbow Lake | 55 | 0 | Gas Turbine | 3 | 2022-04-01 16:00 | 2018-11-16 09:00 | 2019-09-10 21:43
P2194 FortisAlberta East Crossfield 64S DER Solar | 1 | BTF | 57-Airdrie | 1.6 | 0 | Solar | 5 | 2021-07-15 16:00 | 2019-01-04 10:00 | 2019-09-12 21:39
P2096 CKPC Petrochemical Facility | 1 | Connection | 33-Fort Saskatchewan | 0 | 30 | Load | 3 | 2023-07-31 16:00 | 2018-05-24 10:00 | 2019-09-13 16:20
P2212 RESC Rattlesnake Ridge MPC Wind | 1 | Connection | 04-Medicine Hat | 150 | 1 | Wind | 4 | 2021-07-30 16:00 | 2019-02-28 10:00 | 2019-09-23 06:00
P2031 ATCO M.D. of Greenview Load | 1 | Connection | 22-Grande Cache | 0 | 20 | Load | 3 | 2021-12-27 16:00 | 2018-01-02 10:00 | 2019-10-04 18:02
P2216 FortisAlberta Chappice Lake 649S DER Solar | 1 | BTF | 04-Medicine Hat | 10.5 | 0 | Solar | 3 | 2020-12-01 16:00 | 2019-03-22 10:00 | 2019-10-15 06:00
P2266 ATCO Seal Lake 869S DER Solar | 1 | BTF | 19-Peace River | 0 | 0 | Solar | 3 | 2021-05-31 16:00 | 2019-08-14 10:00 | 2019-10-16 06:00
P2231 FortisAlberta Ponoka 331S DER Solar | 1 | BTF | 31-Wetaskiwin | 4 | 0 | Solar | 5 | 2020-08-20 16:00 | 2019-05-03 10:00 | 2019-11-06 20:20
P2214 ATCO Rycroft 730S Battery DER | 1 | BTF | 20-Grande Prairie | 14 | 0 | Battery | 5 | 2020-11-23 16:00 | 2019-03-15 10:00 | 2019-11-06 22:29
P2203 Enbridge South Terminal Gas | 1 | BTF | 60-Edmonton | 19.8 | 0 | Gas | 3 | 2021-02-01 16:00 | 2019-02-07 10:00 | 2019-11-12 23:00
P2192 ENMAX FMC Change | 1 | BTF | 06-Calgary | 0 | 0 | Cogen | 3 | 2020-10-13 16:00 | 2019-01-02 10:00 | 2019-11-21 23:00
P2240 FortisAlberta 198S Blackfalds DER Gas Phase 2 | 1 | BTF | 35-Red Deer | 0 | 0 | Gas | 3 | 2020-08-01 | 2019-05-23 10:00 | 2019-11-25 07:00
P2119 FortisAlberta Coleman Area Reliability | 1 | Connection | 53-Fort Macleod | 0 | 0 | Other | 3 | 2021-12-01 16:00 | 2018-07-04 10:00 | 2019-11-27 07:00
P2241 FortisAlberta 368S Burdett DER Solar | 1 | BTF | 52-Vauxhall | 15 | 0 | Solar | 5 | 2020-11-02 16:00 | 2019-06-05 10:00 | 2019-12-16 22:04
P2262 Suncor ISDF MacKay River 874S Change | 1 | BTF | 25-Fort McMurray | 0 | 10 | Other | 3 | 2022-04-01 16:00 | 2019-07-31 10:00 | 2020-01-03 16:15
P2239 CMH Unit 17 Gas | 1 | BTF | 04-Medicine Hat | 0 | 0 | Gas Turbine | 3 | 2021-07-30 16:00 | 2019-05-03 10:00 | 2020-02-05 17:07
P2280 ATCO Germain 950S Contract Change | 1 | Contract | 25-Fort McMurray | 0 | -4 | DTS | 3 | 2020-10-01 16:00 | 2019-09-25 10:00 | 2020-02-06 07:00
P1978 ATCO Michichi DER Solar | 1 | BTF | 42-Hanna | 61 | 0 | Solar | 3 | 2021-04-01 16:00 | 2017-06-20 10:00 | 2020-02-28 20:53
P2195 FortisAlberta Bassano 435S DER Solar | 1 | BTF | 47-Brooks | 9.3 | 0 | Solar | 3 | 2021-09-01 10:00 | 2019-01-07 10:00 | 2020-04-17 14:38
P2306 FortisAlberta Obed 411S Contact Change | 1 | Contract | 29-Hinton/Edson | 0 | -0.9 | DTS | 3 | 2020-07-01 16:00 | 2020-01-06 10:00 | 2020-04-20 23:23
P2133 EDTI Southeast Edmonton Area Load and Reliability | 1 | Connection | 60-Edmonton | 0 | 31 | Load | 3 | 2022-03-14 16:00 | 2018-08-07 10:00 | 2020-04-21 06:00
P2320 Suncor Firebag Change | 1 | BTF | 25-Fort McMurray | 0 | 0 | Equipment Change | 3 | 2021-04-01 16:00 | 2020-01-30 10:00 | 2020-04-28 22:00
P2233 FortisAlberta Jenner 275S Change | 1 | BTF | 48-Empress | 0 | 0 | Equipment Change | 5 | 2021-04-01 17:00 | 2019-05-07 10:00 | 2020-04-30 03:02
P2199 FortisAlberta Buffalo Atlee Cluster 2 | 1 | BTF | 48-Empress | 13.8 | 0 | Wind | 5 | 2021-12-01 17:00 | 2019-01-28 10:00 | 2020-05-06 06:00
P2102 EPC East Calgary Area Reliability | 1 | Connection | 06-Calgary | 0 | 26 | Load | 3 | 2021-07-30 16:00 | 2018-06-07 10:00 | 2020-05-12 21:28
P2076 ATCO Thornton 2091S Contract Change | 1 | Contract | 22-Grande Cache | 0 | 12.1 | DTS | 3 | 2021-12-27 16:00 | 2018-04-09 10:00 | 2020-05-12 21:55
P2327 Suncor STG4 Modification | 1 | BTF | 25-Fort McMurray | 0 | 0 | Equipment Change | 3 | 2020-10-13 16:00 | 2020-02-13 10:00 | 2020-05-14 13:32
P2253 FortisAlberta Riverbend 618S Contract Change | 1 | Contract | 54-Lethbridge | 0 | 7.6 | DTS | 3 | 2020-07-01 16:00 | 2019-07-03 10:00 | 2020-05-16 00:13
P2332 Syncrude Aurora G20 Modification | 1 | BTF | 25-Fort McMurray | 0 | 0 | Gas Turbine | 3 | 2020-08-15 | 2020-02-24 10:00 | 2020-05-22 22:00
P2284 FortisAlberta Cutting Lake 227S DER Gas | 1 | BTF | 47-Brooks | 7.5 | 0 | Gas | 3 | 2021-11-15 10:00 | 2019-09-30 10:00 | 2020-06-04 16:50
P2267 FortisAlberta Cheviot 101S Contract Change | 1 | Contract | 29-Hinton/Edson | 0 | -8 | DTS | 3 | 2020-10-01 16:00 | 2019-08-15 10:00 | 2020-06-11 06:00
P2179 ATCO 9L32/66 Change | 1 | Connection | 25-Fort McMurray | 0 | 0 | Equipment Change | 3 | 2022-02-10 16:00 | 2018-11-09 09:00 | 2020-06-11 21:41
P2279 CNRL Primrose East 641S Gas | 1 | BTF | 28-Cold Lake | 0 | 0 | Gas Turbine | 3 | 2021-07-01 16:00 | 2019-09-19 10:00 | 2020-06-16 14:31
P2293 FortisAlberta East Crossfield 64S DER Wasteheat | 1 | BTF | 57-Airdrie | 9.5 | 0 | Wasteheat | 3 | 2022-11-01 16:00 | 2019-10-28 10:00 | 2020-06-18 21:58
BTF denotes a behind the fence project and is not governed by the Connection Process. DTS and STS project types denote active contract change requests and are not governed by the Connection Process.