## AESO Connection Pro - Data List
Position | Project | Subproject | Project Type | Planning Area | STS MW Change | DTS MW Change | MW Type | Process Stage | Planned ISD | Applied On | Entered Queue
1 | P0513 Pteragen Peace Butte Wind Farm | 1 | Connection | 4-Medicine Hat | 119.7 | 0.1 | Wind | 5 | 2019-12-01 16:00 | 2005-10-14 | 2010-08-31 06:00
2 | P0462 Enel Alberta Castle Rock Wind Farm | 2 | Connection | 53-Fort Macleod | 30.6 | 0 | Wind | 5 | 2019-06-30 16:00 | 2005-01-05 | 2010-08-31 06:00
3 | P0479 Naturener Wild Rose 1 Wind Farm | 1 | Connection | 4-Medicine Hat | 217.6 | 4 | Wind | 5 | 2019-07-15 16:00 | 2005-05-12 | 2010-08-31 06:00
4 | P0515 Heritage Wind Energy Centre | 1 | Connection | 53-Fort Macleod | 300 | 0 | Wind | 3 | 2020-09-01 16:00 | 2005-09-22 | 2010-08-31 06:00
5 | P0524 Enel Alberta Riverview Wind Farm | 1 | Connection | 53-Fort Macleod | 115 | 1 | Wind | 4 | 2019-06-30 | 2006-01-25 | 2010-08-31 06:00
6 | P0580 Windy Point WAGF | 1 | Connection | 53-Fort Macleod | 63 | 0.6 | Wind | 4 | 2020-10-01 16:00 | 2006-05-12 | 2010-08-31 06:00
7 | P0635 Suncor Hand Hills Wind Energy Project | 1 | Connection | 42-Hanna | 80 | 0.1 | Wind | 5 | 2019-09-01 16:00 | 2006-10-06 | 2010-08-31 06:00
8 | P0678 BluEarth Hand Hills Wind Project | 1 | Connection | 42-Hanna | 78.2 | 0 | Wind | 5 | 2020-09-01 16:00 | 2007-01-15 | 2010-08-31 06:00
9 | P0693 Naturener Wild Rose 2 Wind Farm | 1 | Connection | 4-Medicine Hat | 192 | 4 | Wind | 5 | 2019-07-15 16:00 | 2007-04-03 10:00 | 2010-08-31 06:00
10 | P0851 TransCanada Keystone KXL Pumpstation #2-Eyre | 2 | Connection | 37-Provost | 0 | 25 | Load | 5 | 2020-11-01 | 2008-08-22 | 2010-08-31 06:00
11 | P0851 TransCanada Keystone KXL Pumpstation #2-Eyre | 1 | Connection | 37-Provost | 0 | 0 | Load | 5 | 2020-11-01 | 2008-08-22 | 2010-08-31 06:00
12 | P0863 TransCanada Keystone KXL Pumpstation #3-Current | 1 | Connection | 42-Hanna | 0 | 25 | Load | 5 | 2020-11-01 | 2008-10-08 | 2010-08-31 06:00
13 | P0864 TransCanada Keystone KXL Pumpstation #4-Armitage | 1 | Connection | 42-Hanna | 0 | 25 | Load | 5 | 2020-11-01 | 2008-10-08 | 2010-08-31 06:00
14 | P0865 TransCanada Keystone KXL Pumpstation #5-Cavendish | 1 | Connection | 48-Empress | 0 | 25 | Load | 5 | 2020-11-01 | 2008-10-08 | 2010-08-31 06:00
15 | P1080 Old Elm Wind Farm | 1 | Connection | 55-Glenwood | 60 | 0 | Wind | 3 | 2019-10-31 16:00 | 2010-04-29 | 2011-06-02 06:00
16 | P0937 Irma Wind Power | 1 | Connection | 32-Wainwright | 90 | 3 | Wind | 4 | 2019-07-01 16:00 | 2009-06-11 | 2011-06-30 06:00
17 | P1258 Fortis Alberta Grist Lake (Pike) Substation | 1 | Connection | 25-Fort McMurray | 0 | 23.2 | Load | 5 | 2020-07-01 16:00 | 2011-08-30 10:00 | 2012-08-17 06:00
18 | P1290 Whitetail Peaking Station | 1 | Connection | 19-Peace River | 0 | 1 | Gas | 5 | 2019-07-30 16:00 | 2011-12-07 | 2013-01-31 17:10
19 | P1290 Whitetail Peaking Station | 2 | Connection | 19-Peace River | 200 | 0 | Gas | 5 | 2019-10-25 16:00 | 2011-12-07 | 2013-01-31 17:10
20 | P0803 Mustus Energy Biomass Generator | 1 | Connection | 18-High Level | 41.5 | 0 | Biomass | 5 | 2019-09-30 16:00 | 2011-11-09 | 2013-05-09 16:43
21 | P1250 E.ON Grizzly Bear Wind | 1 | Connection | 13-Lloydminster | 120 | 1.5 | Wind | 5 | 2020-12-15 16:00 | 2011-08-02 10:00 | 2013-06-21 19:29
22 | P1336 BowArk Energy Queenstown Power Plant | 1 | Connection | 45-Strathmore/Blackie | 80 | 0 | Gas Turbine | 5 | 2020-10-01 16:00 | 2012-05-16 10:00 | 2013-06-26 06:00
23 | P1321 Three Creeks Power Plant | 1 | Connection | 19-Peace River | 675 | 10 | Cogen | 5 | 2020-06-01 16:00 | 2012-03-26 | 2013-07-15 17:14
24 | P1289 Maxim Power Deerland Peaking Station | 1 | Connection | 33-Fort Saskatchewan | 185.8 | 0 | Gas Turbine | 5 | 2020-12-01 16:00 | 2011-12-02 | 2013-08-23 06:00
25 | P1404 Cenovus Narrows Lake Substation (Boreal) | 1 | Connection | 25-Fort McMurray | 0 | 35 | Load | 5 | 2020-09-30 16:00 | 2013-01-17 10:00 | 2013-09-20 06:00
26 | P1410 ATCO Heartland Pump Station Connection | 2 | Connection | 56-Vegreville | 0 | 20 | Load | 5 | 2019-12-13 16:00 | 2013-02-05 10:00 | 2014-01-09 07:00
27 | P1412 Trans Mountain Pipeline Gainford Substation 16501S | 1 | Connection | 40-Wabamun | 0 | 11 | Load | 5 | 2020-11-01 16:00 | 2013-02-11 10:00 | 2014-03-03 20:30
28 | P1421 ATCO Power Heartland Generating Station | 1 | Connection | 33-Fort Saskatchewan | 510 | 15 | Combined Cycle | 5 | 2019-11-01 16:00 | 2013-03-11 10:00 | 2014-05-26 06:00
29 | P1442 Fortis New Anthony Henday Substation | 1 | Connection | 60-Edmonton | 0 | 21 | Load | 5 | 2020-11-01 16:00 | 2013-05-02 10:00 | 2014-05-26 06:00
30 | P1460 Fortis New Hornbeck Substation | 1 | Connection | 29-Hinton/Edson | 0 | 18 | Load | 5 | 2020-11-01 16:00 | 2013-07-22 10:00 | 2014-05-27 06:00
31 | P1500 Renewable Energy Service WAGF | 1 | Connection | 53-Fort Macleod | 47 | 1 | Wind | 4 | 2020-12-31 16:00 | 2013-11-18 10:00 | 2014-08-28 06:00
32 | P1440 CP Genesee Generating Units 4 & 5 | 1 | Connection | 60-Edmonton | 0 | 50 | Combined Cycle | 5 | 2021-02-01 16:00 | 2013-04-30 10:00 | 2014-11-25 07:00
33 | P1440 CP Genesee Generating Units 4 & 5 | 2 | Connection | 60-Edmonton | 505 | 0 | Combined Cycle | 5 | 2022-03-31 16:00 | 2013-04-30 10:00 | 2014-11-25 07:00
34 | P1440 CP Genesee Generating Units 4 & 5 | 3 | Connection | 60-Edmonton | 505 | 0 | Combined Cycle | 5 | 2023-03-31 16:00 | 2013-04-30 10:00 | 2014-11-25 07:00
35 | P1516 Enbridge Sunken Lake 221S Transformer Change | 1 | BTF | 37-Provost | 0 | 14 | Load | 3 | 2018-12-01 | 2014-01-23 10:00 | 2014-12-17 07:00
36 | P1505 ATCO City of Grande Prairie New POD | 1 | Connection | 20-Grande Prairie | 0 | 15.5 | Load | 5 | 2020-11-11 16:00 | 2013-12-10 10:00 | 2014-12-19 07:00
37 | P1533 Joss MPC WAGF | 1 | Connection | 48-Empress | 120 | 0 | Wind | 5 | 2019-06-28 16:00 | 2014-03-01 | 2015-01-29 07:00
38 | P1601 ENMAX No 31 Substation 13KV Breakers Addition | 1 | Connection | 6-Calgary | 0 | 0 | Load | 5 | 2018-11-12 16:00 | 2014-09-23 10:00 | 2015-02-02 07:00
39 | P1558 Enbridge New Hardisty Substation | 2 | Connection | 32-Wainwright | 0 | 0 | Load | 5 | 2019-06-01 16:00 | 2014-05-22 | 2015-04-15 06:00
40 | P1567 EDPR Sharp Hills Wind Farm New Facility Generator Capacity | 1 | Connection | 42-Hanna | 300 | 1 | Wind | 5 | 2019-08-01 16:00 | 2014-06-04 | 2015-09-09 06:00
41 | P1566 Calgary Energy Centre Peaking Plant New Generator Capacity | 1 | Connection | 6-Calgary | 150 | 1 | Gas | 5 | 2021-12-01 16:00 | 2014-06-03 | 2015-09-29 06:00
42 | P1603 ATCO Jasper Interconnection Project Capacity Increase | 1 | Connection | 29-Hinton/Edson | 0 | 3.8 | Load | 5 | 2019-12-30 16:00 | 2014-10-10 10:00 | 2015-10-28 06:00
43 | P1649 EPCOR Garneau Area Upgrade | 1 | Connection | 60-Edmonton | 0 | 0 | Load | 4 | 2020-06-30 16:00 | 2015-02-20 10:00 | 2016-02-01 07:00
44 | P1649 EPCOR Garneau Area Upgrade | 2 | Connection | 60-Edmonton | 0 | 20.9 | Load | 4 | 2022-09-30 16:00 | 2015-02-20 10:00 | 2016-02-01 07:00
45 | P1660 Welsch Wind Farm | 1 | Connection | 53-Fort Macleod | 69 | 1 | Wind | 3 | 2020-12-20 16:00 | 2015-03-20 10:00 | 2016-03-07 07:00
46 | P1659 EPCOR Strathcona Capacity Increase | 1 | Connection | 60-Edmonton | 0 | 14.2 | Load | 4 | 2019-10-01 16:00 | 2015-03-19 10:00 | 2016-05-17 06:00
47 | P1658 ATCO Ksituan River 754S Capacity Increase | 1 | Connection | 20-Grande Prairie | 0 | 11.7 | Load | 4 | 2019-02-01 16:00 | 2015-03-17 10:00 | 2016-05-31 19:47
48 | P1695 EPCOR Riverview Substation New POD | 1 | Connection | 60-Edmonton | 0 | 24 | Load | 4 | 2019-10-08 16:00 | 2015-08-24 10:00 | 2016-06-29 15:15
49 | P1794 Fortis Genalta Bellshill DG | 1 | BTF | 36-Alliance/Battle River | 0 | 0 | Gas | 5 | 2019-03-29 16:00 | 2016-05-09 | 2016-08-26 06:00
50 | P1647 Inter Pipeline Strathcona Cogeneration | 1 | Connection | 33-Fort Saskatchewan | 0 | 65 | Cogen | 3 | 2020-03-01 | 2015-02-13 10:00 | 2016-09-09 06:00
51 | P1647 Inter Pipeline Strathcona Cogeneration | 2 | Connection | 33-Fort Saskatchewan | 60 | 0 | Cogen | 3 | 2020-10-01 16:00 | 2015-02-13 10:00 | 2016-09-09 06:00
52 | P1704 Paintearth Wind Power | 1 | Connection | 42-Hanna | 150 | 1 | Wind | 4 | 2019-07-01 16:00 | 2015-10-08 10:00 | 2016-10-05 06:00
53 | P1782 Fortis Provost Reliability | 1 | Connection | 37-Provost | 0 | 0 | Load | 4 | 2020-05-01 16:00 | 2016-04-11 10:00 | 2016-10-07 06:00
54 | P1710 Capital Power Halkirk 2 Wind | 1 | Connection | 36-Alliance/Battle River | 150 | 1.8 | Wind | 3 | 2020-12-01 16:00 | 2015-10-22 10:00 | 2016-10-20 06:00
55 | P1728 RESL McLaughlin Phase 2 BTF | 1 | BTF | 53-Fort Macleod | 40 | 0 | Solar | 3 | 2019-09-30 16:00 | 2016-01-05 10:00 | 2016-10-25 06:00
56 | P1734 Suncor Forty Mile Maleb WAGF | 1 | Connection | 4-Medicine Hat | 200 | 0.3 | Wind | 3 | 2020-09-01 10:00 | 2016-01-06 10:00 | 2016-11-01 06:00
57 | P1698 Joss Jenner WAGF - Phase 2 | 1 | BTF | 48-Empress | 180 | 0 | Wind | 5 | 2019-05-01 16:00 | 2015-09-08 10:00 | 2016-11-02 06:00
58 | P1767 RESC Forty Mile WAGF | 1 | Connection | 4-Medicine Hat | 400 | 0 | Wind | 3 | 2020-06-30 16:00 | 2016-03-09 10:00 | 2016-11-16 07:00
59 | P1787 ENMAX No.7 Substation 138/25KV Transformer Upgrade | 1 | Connection | 6-Calgary | 0 | 0 | Load | 5 | 2018-11-27 16:00 | 2016-04-18 10:00 | 2016-12-01 07:00
60 | P1787 ENMAX No.7 Substation 138/25KV Transformer Upgrade | 2 | Connection | 6-Calgary | 0 | 5 | Load | 5 | 2019-01-24 16:00 | 2016-04-18 10:00 | 2016-12-01 07:00
61 | P1787 ENMAX No.7 Substation 138/25KV Transformer Upgrade | 3 | Connection | 6-Calgary | 0 | 0 | Load | 5 | 2019-03-28 16:00 | 2016-04-18 10:00 | 2016-12-01 07:00
62 | P1718 Wheatland WAGF Project | 1 | Connection | 43-Sheerness | 120 | 0 | Wind | 3 | 2019-12-31 16:00 | 2015-10-30 | 2016-12-16 07:00
63 | P1719 Stirling WAGF Project | 1 | Connection | 54-Lethbridge | 113 | 0 | Wind | 4 | 2019-07-01 16:00 | 2015-10-30 | 2016-12-16 07:00
64 | P1739 Suncor Firebag Generator Reactor Capacity Increase | 1 | BTF | 25-Fort McMurray | 0 | 0 | Other | 5 | 2018-12-17 16:00 | 2016-01-07 10:00 | 2017-01-12 07:00
65 | P1762 EDF EN Vulcan Solar PV | 1 | BTF | 49-Stavely | 100 | 0 | Solar | 5 | 2018-12-01 16:00 | 2016-03-07 10:00 | 2017-01-16 07:00
66 | P1826 Fortis GP Joule Canada Cluny DG | 1 | BTF | 45-Strathmore/Blackie | 1.2 | 0 | Solar | 3 | 2018-10-31 16:00 | 2016-07-29 10:00 | 2017-01-18 07:00
67 | P1696 BluEarth Burdett DG PV | 1 | BTF | 52-Vauxhall | 15 | 0 | Solar | 5 | 2019-05-30 16:00 | 2015-08-27 10:00 | 2017-01-27 07:00
68 | P1897 Fortis Hays 421S DER Solar | 1 | BTF | 52-Vauxhall | 0 | 0 | Solar | 3 | 2019-01-29 16:00 | 2016-11-25 10:00 | 2017-02-06 17:04
69 | P1731 Suncor Hand Hills Wind Project Phase 2 New POS | 1 | BTF | 43-Sheerness | 80 | 0.3 | Wind | 3 | 2019-10-31 16:00 | 2016-01-06 10:00 | 2017-02-09 07:00
70 | P1732 Suncor Hand Hills Solar Project New POS | 1 | BTF | 43-Sheerness | 80 | 0.3 | Solar | 3 | 2019-10-31 16:00 | 2016-01-06 10:00 | 2017-02-09 07:00
71 | P1812 Suncor Forty Mile Granlea WAGF | 1 | Connection | 4-Medicine Hat | 200 | 0.3 | Wind | 3 | 2020-06-01 10:00 | 2016-07-04 10:00 | 2017-02-28 07:00
72 | P1882 TransCanada Scoria 318S Cogen | 1 | BTF | 33-Fort Saskatchewan | 0 | 0 | Cogen | 5 | 2019-01-25 16:00 | 2016-10-26 10:00 | 2017-03-14 06:00
73 | P1756 TPG Canyon Creek PHES Storage Project | 1 | Connection | 29-Hinton/Edson | 75 | 64 | Pumped Storage | 3 | 2021-08-10 16:00 | 2016-03-02 10:00 | 2017-03-23 06:00
74 | P1849 Fortis Burdett 368S DG P/V | 1 | BTF | 52-Vauxhall | 9.5 | 0 | Solar | 3 | 2019-10-30 16:00 | 2016-08-24 10:00 | 2017-03-24 06:00
75 | P1837 Fortis 498S Tilley DG PV | 1 | BTF | 52-Vauxhall | 14 | 0 | Solar | 3 | 2019-06-03 16:00 | 2016-08-05 10:00 | 2017-03-31 06:00
76 | P1838 Fortis 895S Suffield DG PV | 1 | BTF | 4-Medicine Hat | 22 | 0 | Solar | 3 | 2019-06-03 16:00 | 2016-08-05 10:00 | 2017-03-31 06:00
77 | P1831 Fortis 255S Vulcan Faribault Farms DG PV | 1 | BTF | 49-Stavely | 14 | 0 | Solar | 3 | 2020-08-01 16:00 | 2016-08-05 10:00 | 2017-04-21 18:47
78 | P1851 Fortis Monarch 492S DER Solar | 1 | BTF | 54-Lethbridge | 20 | 0 | Solar | 3 | 2020-08-01 16:00 | 2016-08-26 10:00 | 2017-04-21 18:49
79 | P1870 Fortis Stavely 349S DER Solar | 1 | BTF | 49-Stavely | 8.5 | 0 | Solar | 3 | 2020-08-01 16:00 | 2016-10-05 10:00 | 2017-04-21 18:50
80 | P1833 Fortis Tilley 498S DG Gas | 1 | BTF | 47-Brooks | 16 | 0 | Gas | 3 | 2019-11-15 16:00 | 2016-08-05 10:00 | 2017-05-12 06:00
81 | P1777 Invenergy Schuler Windfarm | 1 | Connection | 4-Medicine Hat | 100 | 2 | Wind | 3 | 2020-07-01 16:00 | 2016-03-29 10:00 | 2017-05-15 06:00
82 | P1800 Capital Power Whitla Wind Power Facility | 1 | Connection | 4-Medicine Hat | 201.6 | 3.5 | Wind | 5 | 2019-09-01 | 2016-05-25 10:00 | 2017-05-18 06:00
83 | P1800 Capital Power Whitla Wind Power Facility | 2 | Connection | 4-Medicine Hat | 97.2 | 1 | Wind | 5 | 2020-09-01 16:00 | 2016-05-25 10:00 | 2017-05-18 06:00
84 | P1905 FortisAlberta Fort Macleod Area Reliability | 1 | Connection | 53-Fort Macleod | 0 | 0 | Load | 6 | 2018-11-15 16:00 | 2016-12-20 10:00 | 2017-05-18 06:00
85 | P1903 FortisAlberta East Yellowhead Area Capacity and Reliability Project | 1 | Connection | 29-Hinton/Edson | 0 | 3.9 | Load | 6 | 2018-11-01 16:00 | 2016-12-20 10:00 | 2017-05-26 06:00
86 | P1797 RES Oyen Wind Power | 1 | Connection | 42-Hanna | 350 | 2 | Wind | 3 | 2021-06-30 16:00 | 2016-05-16 | 2017-05-30 20:26
87 | P1898 Pattern Lanfine North Wind | 1 | Connection | 42-Hanna | 145 | 0 | Wind | 3 | 2020-05-01 16:00 | 2016-12-02 10:00 | 2017-06-16 06:00
88 | P1877 Sunset Solar Project | 1 | Connection | 52-Vauxhall | 60 | 0.3 | Solar | 3 | 2020-06-30 16:00 | 2016-10-20 10:00 | 2017-06-27 06:00
89 | P1847 Fortis Coaldale 254S DG P/V | 1 | BTF | 54-Lethbridge | 12 | 0 | Solar | 3 | 2019-03-31 16:00 | 2016-08-23 10:00 | 2017-07-20 21:22
90 | P1850 Fortis Coaldale 254S DER Solar 3 | 1 | BTF | 54-Lethbridge | 22 | 0 | Solar | 3 | 2020-08-01 16:00 | 2016-08-26 10:00 | 2017-07-20 21:22
91 | P1872 Fortis Coaldale 254S DER Solar 2 | 1 | BTF | 54-Lethbridge | 20 | 0 | Solar | 3 | 2019-03-31 16:00 | 2016-10-12 10:00 | 2017-07-24 16:30
92 | P1887 ENGIE Duchess Solar | 1 | Connection | 47-Brooks | 90 | 0.1 | Solar | 3 | 2020-06-30 16:00 | 2016-11-03 10:00 | 2017-07-26 06:00
93 | P1862 Fortis Spring Coulee 385S Solar DG | 1 | BTF | 55-Glenwood | 28.5 | 0 | Solar | 5 | 2019-04-30 16:00 | 2016-09-28 10:00 | 2017-07-28 18:13
94 | P1879 Perimeter Claresholm Solar | 1 | Connection | 49-Stavely | 130 | 0.6 | Solar | 3 | 2020-06-30 16:00 | 2016-10-25 10:00 | 2017-08-03 06:00
95 | P1839 Fortis 421S Hays DG PV | 1 | BTF | 52-Vauxhall | 15 | 0 | Solar | 3 | 2019-06-07 16:00 | 2016-08-05 10:00 | 2017-08-11 06:00
96 | P1842 Fortis 158S Vauxhall DG PV | 1 | BTF | 52-Vauxhall | 11 | 0 | Solar | 3 | 2019-06-03 16:00 | 2016-08-05 10:00 | 2017-08-11 06:00
97 | P1869 Fortis Enchant 447S DER Solar | 1 | BTF | 52-Vauxhall | 68.2 | 0 | Solar | 5 | 2019-08-31 16:00 | 2016-10-03 10:00 | 2017-08-11 06:00
98 | P1878 Fortis Krafte 257S Hull DER Solar | 1 | BTF | 52-Vauxhall | 24.5 | 0 | Solar | 5 | 2019-07-30 16:00 | 2016-10-24 10:00 | 2017-08-11 06:00
99 | P1902 FortisAlberta Fincastle Area Capacity and Reliability Project | 1 | Connection | 52-Vauxhall | 0 | 11.1 | Load | 4 | 2019-06-01 16:00 | 2016-12-20 10:00 | 2017-08-31 22:00
100 | P1864 BowArk Drywood Gas Generator | 1 | Connection | 45-Strathmore/Blackie | 38 | 1 | Gas | 3 | 2020-10-01 10:00 | 2016-09-30 10:00 | 2017-09-08 22:00
101 | P1766 FortisAlberta Warner-Conrad Area Upgrade | 1 | Connection | 55-Glenwood | 0 | 3.5 | Load | 5 | 2019-06-14 16:00 | 2016-03-09 10:00 | 2017-09-26 06:00
102 | P1904 FortisAlberta Crossfield Area Capacity and Reliability Project | 1 | Connection | 57-Airdrie | 0 | 4.9 | Load | 5 | 2019-11-01 16:00 | 2016-12-20 10:00 | 2017-09-28 06:00
103 | P1908 TransAlta Cowley Ridge 1 Wind | 1 | BTF | 53-Fort Macleod | 21 | 0.5 | Wind | 3 | 2019-04-30 16:00 | 2016-12-22 10:00 | 2017-10-04 22:00
104 | P1917 FortisAlberta West Brooks DER Solar | 1 | BTF | 47-Brooks | 19.2 | 0 | Solar | 5 | 2019-10-15 10:00 | 2017-02-06 10:00 | 2017-10-17 06:00
105 | P1979 ATCO Monitor DER Solar | 1 | BTF | 42-Hanna | 4 | 0 | Solar | 3 | 2019-05-01 16:00 | 2017-06-20 10:00 | 2017-10-19 06:00
106 | P1907 FortisAlberta Vulcan-Stavely Area Capacity and Reliability | 1 | Connection | 49-Stavely | 0 | 3.5 | Load | 5 | 2019-11-01 16:00 | 2017-01-18 10:00 | 2017-10-19 22:00
107 | P1982 EDTI DG Solar BTF | 1 | BTF | 60-Edmonton | 0 | 0 | Solar | 3 | 2019-11-30 | 2017-07-07 10:00 | 2017-10-24 06:00
108 | P1932 FortisAlberta Namaka DER Solar | 1 | BTF | 45-Strathmore/Blackie | 15.5 | 0 | Solar | 3 | 2019-06-28 16:00 | 2017-04-10 10:00 | 2017-10-25 06:00
109 | P1964 FortisAlberta Killarney Lake DER Solar | 1 | BTF | 37-Provost | 0 | 0 | Solar | 3 | 2019-01-01 16:00 | 2017-05-22 10:00 | 2017-11-24 07:00
110 | P1922 FortisAlberta Vauxhall Solar DER | 1 | BTF | 52-Vauxhall | 22 | 0 | Solar | 5 | 2019-06-30 | 2017-03-14 10:00 | 2017-12-06 22:40
111 | P1909 TransAlta Garden Plain Wind | 1 | Connection | 42-Hanna | 130 | 4 | Wind | 3 | 2020-02-21 16:00 | 2016-12-22 10:00 | 2017-12-07 07:00
112 | P1853 Fortis Buffalo Atlee Cluster 1 WAGF | 1 | BTF | 48-Empress | 18.3 | 0 | Wind | 5 | 2019-03-01 16:00 | 2016-08-30 10:00 | 2017-12-07 18:13
113 | P1892 Fortis Buffalo Atlee Cluster 3 WAGF DER | 1 | BTF | 48-Empress | 17.3 | 0 | Wind | 5 | 2019-03-18 16:00 | 2016-11-15 10:00 | 2017-12-07 18:16
114 | P1923 CNRL Kirby North Load | 1 | Connection | 25-Fort McMurray | 0 | 29 | Load | 4 | 2019-03-01 16:00 | 2017-03-21 10:00 | 2017-12-08 23:33
115 | P1915 Acciona Energy Glenwood Area Wind | 1 | Connection | 55-Glenwood | 119.7 | 3.1 | Wind | 3 | 2019-09-01 16:00 | 2017-02-02 10:00 | 2017-12-15 18:24
116 | P1852 Fortis Stirling 67S DG P/V | 1 | BTF | 55-Glenwood | 17.4 | 0 | Solar | 5 | 2019-03-30 | 2016-08-30 10:00 | 2017-12-21 17:34
117 | P1984 FortisAlberta Gleichen DG Solar | 1 | BTF | 45-Strathmore/Blackie | 17 | 0 | Solar | 3 | 2019-06-28 16:00 | 2017-07-17 10:00 | 2018-02-14 07:00
118 | P1980 ENMAX North 69KV Reliability | 1 | Connection | 6-Calgary | 0 | 0 | Other | 5 | 2019-02-01 16:00 | 2017-07-06 10:00 | 2018-03-05 07:00
119 | P1840 Fortis 275S Jenner Solar DER | 1 | BTF | 48-Empress | 23 | 0 | Solar | 5 | 2019-06-03 16:00 | 2016-08-05 10:00 | 2018-03-09 23:03
120 | P1918 FortisAlberta Conrad DER Solar 1 | 1 | BTF | 52-Vauxhall | 18.4 | 0 | Solar | 3 | 2019-07-15 16:00 | 2017-02-06 10:00 | 2018-03-16 06:00
121 | P1959 FortisAlberta Conrad DER Solar 2 | 1 | BTF | 52-Vauxhall | 22.5 | 0 | Solar | 3 | 2019-11-29 16:00 | 2017-05-08 10:00 | 2018-03-16 06:00
122 | P1967 FortisAlberta Jenner 275S DER | 1 | BTF | 48-Empress | 16.1 | 0 | Gas Turbine | 5 | 2019-07-15 16:00 | 2017-06-06 10:00 | 2018-03-27 06:00
123 | P2046 ATCO Mowat 2033S DER | 1 | BTF | 20-Grande Prairie | 0 | 0 | Gas | 3 | 2018-12-07 16:00 | 2018-01-23 | 2018-03-28 17:27
124 | P2015 Coalspur Vista Coal Mine Load | 1 | Connection | 29-Hinton/Edson | 0 | 23 | Other | 5 | 2018-11-18 | 2017-11-06 10:00 | 2018-04-05 06:00
125 | P2012 Keyera West Pembina 359S Gas Turbine | 1 | BTF | 30-Drayton Valley | 4.9 | 0 | Gas Turbine | 3 | 2019-05-15 16:00 | 2017-10-25 10:00 | 2018-04-20 21:43
126 | P1875 EDF EN Red Rock WAGF | 1 | Connection | 4-Medicine Hat | 250 | 3.6 | Wind | 3 | 2021-05-01 16:00 | 2016-10-14 10:00 | 2018-05-03 06:00
127 | P1927 Solar Krafte Brooks | 1 | Connection | 47-Brooks | 400 | 1 | Solar | 3 | 2020-04-01 16:00 | 2017-03-23 10:00 | 2018-05-03 17:10
128 | P1962 FortisAlberta Provost DER Solar | 1 | BTF | 37-Provost | 0 | 0 | Solar | 3 | 2019-01-01 16:00 | 2017-05-10 10:00 | 2018-05-09 14:16
129 | P1961 FortisAlberta Wainwright DER Solar | 1 | BTF | 32-Wainwright | 0 | 0 | Solar | 3 | 2019-01-01 16:00 | 2017-05-10 10:00 | 2018-05-09 14:17
130 | P2023 FortisAlberta Kananaskis Area Reliability | 1 | Connection | 44-Seebe | 0 | 4.7 | Load | 3 | 2019-11-01 16:00 | 2017-11-22 10:00 | 2018-05-14 22:00
131 | P2035 FortisAlberta Willesdengreen DER Gas Turbine | 1 | BTF | 30-Drayton Valley | 5 | 0 | Gas Turbine | 3 | 2018-11-01 16:00 | 2018-01-02 10:00 | 2018-05-28 18:57
132 | P1974 FortisAlberta Duchess DER Solar | 1 | BTF | 47-Brooks | 10.1 | 0 | Solar | 3 | 2019-03-31 | 2017-06-14 10:00 | 2018-06-01 06:00
133 | P2000 ENMAX Taber BTF Wind | 1 | BTF | 52-Vauxhall | 21 | 0 | Wind | 3 | 2020-12-01 16:00 | 2017-09-18 10:00 | 2018-06-21 06:00
134 | P1865 Fortis Warner 344S DER Solar | 1 | BTF | 55-Glenwood | 16.5 | 0 | Solar | 5 | 2019-05-15 16:00 | 2016-10-03 10:00 | 2018-06-22 06:00
135 | P1995 ATCO Coronation 773S Solar DG | 1 | BTF | 42-Hanna | 12 | 0 | Solar | 3 | 2019-03-15 16:00 | 2017-08-30 10:00 | 2018-06-29 20:33
136 | P1976 FortisAlberta Brooks DER Solar | 1 | BTF | 47-Brooks | 13.7 | 0 | Solar | 3 | 2019-08-05 16:00 | 2017-06-20 10:00 | 2018-07-09 06:00
137 | P1934 FortisAlberta Empress DER Solar | 1 | BTF | 48-Empress | 20.5 | 0 | Solar | 3 | 2019-05-01 16:00 | 2017-04-12 10:00 | 2018-08-22 16:37
138 | P1960 FortisAlberta Bassano DER Solar | 1 | BTF | 47-Brooks | 0 | 0 | Solar | 3 | 2019-01-01 16:00 | 2017-05-10 10:00 | 2018-08-24 15:24
139 | P2148 ATCO Germain 950S Contract Change | 1 | Contract | 25-Fort McMurray | 0 | 37 | DTS | 5 | 2018-12-01 | 2018-08-31 10:00 | 2018-09-10 06:00
140 | P2009 Greengate Travers MPC Solar | 1 | Connection | 49-Stavely | 400 | 0.5 | Solar | 3 | 2020-12-01 16:00 | 2017-10-20 10:00 | 2018-09-18 06:00
141 | P2028 FortisAlberta Barrhead-Westlock Area Reliability | 1 | Connection | 27-Athabasca/Lac La Biche, 40-Wabamun | 0 | 0 | Load | 3 | 2020-12-01 16:00 | 2017-12-05 10:00 | 2018-09-21 06:00
142 | P2139 FortisAlberta Jumping Pound 271S Contract Change | 1 | Contract | 44-Seebe | 0 | -1.7 | DTS | 5 | 2019-01-29 16:00 | 2018-08-20 10:00 | 2018-09-24 22:00
143 | P2154 ATCO Waddell 907S Contract Change | 1 | Contract | 25-Fort McMurray | 0 | 3.3 | DTS | 5 | 2019-01-01 16:00 | 2018-09-14 10:00 | 2019-01-22 23:00
BTF denotes a behind the fence project and is not governed by the Connection Process. DTS and STS project types denote active contract change requests and are not governed by the Connection Process.