## Connection Project List
Project Information | [6 empty] | Energization 1 |  |  | Energization 2 |  |  | Energization 3
Project Name | Planning Area | Project Type | MW Type | Stage | Inclusion | Applied On | STS MW | DTS MW | ISD | STS MW | DTS MW | ISD | STS MW | DTS MW | ISD
Active
P0693 Wild Rose 2 Wind Farm | 04-Medicine Hat | Connection | Wind | 5 | Yes | 2007-05-01 10:00 | 192 | 4 | 2023-06-30
P1250 Wild Run Grizzly Bear Wind | 13-Lloydminster | Connection | Wind | 6 | Yes | 2011-08-02 10:00 | 120 | 1.5 | 2022-12-01
P1567 EDPR Sharp Hills Wind Farm | 42-Hanna | Connection | Wind | 5 | Yes | 2014-06-04 | 0 | 0.5 | 2022-12-16 | 288.9 | 0 | 2023-08-15
P1649 EPCOR Garneau Area Upgrade | 60-Edmonton | Connection | Load | 5 | Yes | 2015-02-20 10:00 | 0 | 0 | 2022-04-08 | 0 | 0 | 2022-06-14 | 0 | 0 | 2023-03-31
P1704 Paintearth Wind Power | 42-Hanna | Connection | Wind | 5 | Yes | 2015-10-08 10:00 | 150 | 1 | 2023-07-28
P1719 Stirling WAGF Project | 54-Lethbridge | Connection | Wind | 5 | Yes | 2015-10-30 | 113 | 1 | 2023-06-30
P1756 TPG Canyon Creek PHES Storage Project | 29-Hinton/Edson | Connection | Pumped Hydro Storage | 3 | No | 2016-03-02 10:00 | 75 | 64 | 2024-12-01 |  |  | 2025-05-01
P1824 Lone Pine MPC Wind | 42-Hanna | Connection | Wind | 2 | No | 2016-07-28 10:00 | 466 | 1 | 2024-12-13
P1828 HEP Energy Alderson MPC Solar | 04-Medicine Hat | Connection | Solar | 3 | No | 2016-07-29 10:00 | 100 | 1 | 2024-12-02
P1853 Fortis Buffalo Atlee Cluster 1 WAGF | 48-Empress | BTF | Wind | 3 | Yes | 2016-08-30 10:00 | 12.3 | 0 | 2023-04-14
P1862 Fortis Spring Coulee 385S Solar DG | 55-Glenwood | BTF | Solar | 5 | Yes | 2016-09-28 10:00 | 28.5 | 0 | 2023-09-15
P1863 Pihew Waciy | 28-Cold Lake | Connection | Wind | 3 | No | 2016-09-16 10:00 | 100 | 1 | 2024-08-30
P1870 Fortis Stavely 349S DER Solar | 49-Stavely | BTF | Solar | 5 | Yes | 2016-10-05 10:00 | 13 | 0 | 2023-03-01
P1892 Fortis Buffalo Atlee Cluster 3 WAGF DER | 48-Empress | BTF | Wind | 3 | Yes | 2016-11-15 10:00 | 4.6 | 0 | 2023-04-14
P1926 Solar Krafte Vauxhall | 52-Vauxhall | Connection | Solar | 3 | No | 2017-03-23 10:00 | 150 | 0.375 | 2024-06-01
P1927 Solar Krafte Brooks | 47-Brooks | Connection | Solar | 4 | Yes | 2017-03-23 10:00 | 360 | 0.99 | 2023-12-01
P1978 ATCO Michichi DER Solar | 42-Hanna | BTF | Solar | 5 | Yes | 2017-06-20 10:00 | 61 | 0 | 2023-11-01
P1984 FortisAlberta Gleichen DG Solar | 45-Strathmore/Blackie | BTF | Solar | 3 | No | 2017-07-17 10:00 | 11.9 | 0 | 2023-10-31
P1987 Rainier MPC Solar | 47-Brooks | Connection | Solar | 2 | No | 2017-07-28 10:00 | 450 | 1.12 | 2024-06-04
P2008 Greengate Lathom MPC Solar | 47-Brooks | Connection | Solar | 3 | No | 2017-10-20 10:00 | 120 | 0.5 | 2023-06-01
P2031 ATCO M.D. of Greenview Load | 22-Grande Cache | Connection | Load | 3 | No | 2018-01-02 10:00 | 0 | 33.2 | 2024-12-01
P2032 Cascade Combined Cycle | 29-Hinton/Edson | Connection | Gas | 5 | Yes | 2018-01-02 10:00 | 0 | 0 | 2022-03-01 | 0 | 11.5 | 2022-12-10 | 900 | 0
P2034 Cold Lake Area Energy Centre | 28-Cold Lake | Connection | Cogen | 3 | No | 2018-01-02 10:00 | 100 | 3 | 2025-04-01
P2065 Wild Run Grizzly Bear Wind Phase 2 | 13-Lloydminster | BTF | Wind | 6 | Yes | 2018-03-09 10:00 | 32.1 | 0 | 2022-12-01
P2076 ATCO Thornton 2091S Contract Change | 22-Grande Cache | Contract | DTS | 3 | Yes | 2018-04-09 10:00 | 0 | 12.1 | 2025-10-01
P2082 Suncor Base Plant Cogen | 25-Fort McMurray | Connection | Cogen | 5 | Yes | 2018-04-24 10:00 | 806 | 0 | 2023-04-15 |  |  | 2023-09-01 |  |  | 2024-03-01
P2091 EDP Renewables Blue Bridge Solar | 48-Empress | Connection | Solar | 2 | No | 2018-05-22 10:00 | 150 | 5 | 2025-08-01
P2102 EPC East Calgary Area Reliability | 06-Calgary | Connection | Load | 4 | No | 2018-06-07 10:00 | 0 | 26 | 2024-10-28
P2122 Cypress Wind Project Connection | 04-Medicine Hat | Connection | Wind | 5 | Yes | 2018-07-12 10:00 | 195.9 | 2.2 | 2022-08-31 |  |  | 2023-01-03
P2134 CNRL Muskeg River 847S Change | 25-Fort McMurray | BTF | Equipment Change | 5 | Yes | 2018-08-07 10:00 | 0 | 0 | 2023-04-01
P2136 FortisAlberta Brazeau Area Reliability | 30-Drayton Valley | Connection | Load | 2 | No | 2018-08-09 10:00 | 0 | 5.4 | 2025-01-10
P2137 Enerfin Winnifred MPC Wind | 04-Medicine Hat | Connection | Wind | 4 | Yes | 2018-08-10 10:00 | 90 | 1 | 2024-10-01
P2179 CNRL 9L32/66 Change | 25-Fort McMurray | Connection | Equipment Change | 5 | Yes | 2018-11-09 09:00 | 0 | 0 | 2023-03-31
P2192 ENMAX FMC Change | 06-Calgary | BTF | Cogen | 5 | Yes | 2019-01-02 10:00 | 4.99 | 0 | 2023-12-15
P2196 Grand Prairie MPC Gas | 20-Grande Prairie | Connection | Gas | 3 | No | 2019-01-11 10:00 | 400 | 5 | 2024-06-01
P2199 FortisAlberta Buffalo Atlee Cluster 2 | 48-Empress | BTF | Wind | 3 | Yes | 2019-01-28 10:00 | 13.8 | 0 | 2023-04-14
P2201 ENMAX SS-1 Substation Change | 06-Calgary | BTF | Equipment Change | 3 | No | 2019-01-30 10:00 | 0 | 0 | 2024-01-01
P2218 ENGIE Duchess Solar | 47-Brooks | Connection | Solar | 3 | No | 2019-04-01 10:00 | 90 | 0.11 | 2023-09-01
P2232 ENGIE Buffalo Trail North Wind | 04-Medicine Hat | Connection | Wind | 4 | No | 2019-05-03 10:00 | 200 | 6 | 2024-08-01
P2233 FortisAlberta Jenner 275S Change | 48-Empress | BTF | Equipment Change | 5 | Yes | 2019-05-07 10:00 | 0 | 0 | 2021-05-25 | 0 | 0 | 2023-01-27
P2237 RESC Forty Mile MPC Wind | 04-Medicine Hat | Connection | Wind | 4 | Yes | 2019-05-09 10:00 | 266 | 10 | 2023-09-01
P2247 Buffalo Plains MPC Wind | 47-Brooks | Connection | Wind | 5 | Yes | 2019-06-28 10:00 | 466 | 2 | 2023-04-17 |  |  | 2023-07-24
P2248 ATCO Michichi Creek 802S DER Solar | 42-Hanna | BTF | Solar + Storage | 5 | No | 2019-06-26 10:00 | 13.5 | 0 | 2023-04-01
P2249 FortisAlberta Empress 394S DER Solar 1 | 48-Empress | BTF | Solar | 5 | Yes | 2019-06-28 10:00 | 22 | 0 | 2023-05-01
P2250 FortisAlberta Empress 394S DER Solar 2 | 48-Empress | BTF | Solar | 5 | Yes | 2019-06-28 10:00 | 15.5 | 0 | 2023-05-01
P2259 FortisAlberta Metiskow 648S DER Solar | 37-Provost | BTF | Solar + Storage | 3 | No | 2019-07-17 10:00 | 22 | 0 | 2023-11-01
P2279 CNRL Primrose East 641S Gas | 28-Cold Lake | BTF | Gas | 5 | Yes | 2019-09-19 10:00 | 0 | 0 | 2024-06-30
P2289 Heartland Scotford Change | 33-Fort Saskatchewan | BTF | Equipment Change | 6 | Yes | 2019-10-23 10:00 | 0 | 0 | 2023-03-22
P2292 FortisAlberta Killarney Lake 267S DER Solar/Battery Storage | 37-Provost | BTF | Solar + Storage | 3 | No | 2019-10-28 10:00 | 18 | 0 | 2023-11-01
P2296 ATCO Willow Lake 2009S Contract Change | 25-Fort McMurray | Contract | DTS | 6 | Yes | 2019-11-22 10:00 | 0 | 25.6 | 2025-01-01
P2300 Enterprise MPC Solar | 49-Stavely | Connection | Solar | 5 | Yes | 2019-11-21 10:00 | 65 | 1 | 2023-06-30
P2314 FortisAlberta Joffre 535S DER Solar | 35-Red Deer | BTF | Solar | 5 | No | 2020-01-17 10:00 | 22.8 | 0 | 2023-06-01
P2315 FortisAlberta Joffre 535S DER Solar 2 | 35-Red Deer | BTF | Solar | 5 | No | 2020-01-17 10:00 | 18 | 0 | 2023-06-01
P2318 EDF North Slope Solar | 04-Medicine Hat | Connection | Solar | 2 | No | 2020-01-29 10:00 | 200 | 3 | 2023-08-01
P2334 TCE Saddlebrook Solar Storage | 46-High River | Connection | Solar + Storage | 4 | Yes | 2020-03-20 10:00 | 81 | 0.2 | 2023-08-31
P2335 Fortis Vulcan 255S DER Solar | 49-Stavely | BTF | Solar | 5 | Yes | 2020-03-09 10:00 | 12.6 | 0 | 2023-06-30
P2337 Dunmore Solar | 04-Medicine Hat | Connection | Solar | 5 | Yes | 2020-03-16 10:00 | 216 | 0.5 | 2024-12-01
P2342 EDF Bull Trail Wind | 04-Medicine Hat | Connection | Wind | 3 | No | 2020-03-30 10:00 | 300 | 4 | 2023-09-01
P2346 ATCO Vilna 777S DER Solar | 56-Vegreville | BTF | Solar | 5 | No | 2020-04-09 10:00 | 2.7 | 0 | 2023-02-01
P2347 Forty Mile Granlea Solar Phase 2 | 04-Medicine Hat | BTF | Solar | 5 | Yes | 2020-04-24 10:00 | 220 | 0.5 | 2023-11-17
P2348 BluEarth Wheatcrest MPC Solar | 52-Vauxhall | Connection | Solar | 4 | Yes | 2020-05-04 10:00 | 50 | 0.15 | 2023-03-15
P2352 ATCO Ethel Lake 717S DER Wasteheat | 28-Cold Lake | BTF | Wasteheat | 5 | Yes | 2020-05-07 10:00 | 0 | 0 | 2024-09-01
P2353 Fortis Castle Meridian DER Wind | 53-Fort Macleod | Connection | Wind | 2 | No | 2020-05-21 10:00 | 22.4 | 0 | 2022-12-31
P2354 ENMAX FMC DER Cogen | 06-Calgary | BTF | Cogen | 5 | No | 2020-05-21 10:00 | 4.99 | 0 | 2023-02-15 |  |  | 2023-08-15
P2356 RESC Oyen MPC Wind | 42-Hanna | Connection | Wind | 3 | No | 2020-06-18 10:00 | 250 | 1 | 2024-12-02
P2361 ATCO Youngstown 772S DER Solar | 42-Hanna | BTF | Solar | 3 | Yes | 2020-07-15 10:00 | 5.8 | 0 | 2023-04-01
P2369 ATCO Anderson 801S DER Solar | 43-Sheerness | BTF | Solar | 2 | No | 2020-08-04 10:00 | 9.8 | 0 | 2024-04-12
P2371 Fortis High River 65S DER Gas | 46-High River | BTF | Gas | 3 | No | 2020-08-12 10:00 | 6.9 | 0 | 2023-09-01
P2378 RESC Nova MPC Solar | 45-Strathmore/Blackie | Connection | Solar | 4 | No | 2020-09-08 10:00 | 150 | 1 | 2023-07-14
P2382 ATCO Mariana Lake Load | 25-Fort McMurray | Connection | Load | 5 | Yes | 2020-09-14 10:00 | 0 | 5 | 2023-02-01 | 0 | 23.8 | 2023-05-01
P2383 CP Genesee Unit 6 Gas | 40-Wabamun | Connection | Gas | 4 | Yes | 2020-09-17 10:00 | 430 | 0 | 2023-12-22
P2389 CP Genesee Unit 1 Repower ST | 40-Wabamun | BTF | Gas | 5 | Yes | 2020-10-13 10:00 | -100 | 0 | 2023-12-22
P2390 Fortis Gulf Robb 414S Contract Change | 29-Hinton/Edson | Contract | DTS | 3 | No | 2020-10-14 10:00 | 0 | -0.93 | 2025-11-01
P2391 Old Elm Wind | 55-Glenwood | Connection | Wind | 2 | No | 2020-10-14 10:00 | 60 | 0.5 | 2023-12-31
P2392 Nutrien Redwater Cogen | 33-Fort Saskatchewan | BTF | Cogen | 5 | Yes | 2020-10-21 10:00 | 0 | 0 | 2023-08-30
P2396 Georgetown Solar | 45-Strathmore/Blackie | Connection | Solar | 3 | No | 2020-11-12 10:00 | 230 | 1 | 2023-08-01
P2405 Sollair Solar | 57-Airdrie | Connection | Solar | 4 | No | 2020-11-30 10:00 | 75 | 0.5 | 2023-03-01
P2407 Fortis Kirby 651S Contract Change | 27-Athabasca/Lac La Biche | Contract | DTS | 3 | No | 2020-12-11 10:00 | 0 | -5 | 2026-01-01
P2409 CP Genesee Unit 7 Gas | 40-Wabamun | Connection | Gas | 3 | Yes | 2021-01-04 10:00 | 430 | 3 | 2023-12-22
P2410 CP Genesee 2 Repower ST | 40-Wabamun | BTF | Gas | 5 | Yes | 2021-01-04 10:00 | -100 | 0 | 2024-01-15
P2411 Greengate Jurassic MPC Solar Battery | 48-Empress | Connection | Solar + Storage | 3 | No | 2021-01-04 10:00 | 300 | 1.5 | 2023-12-31
P2412 Fortis Buffalo Atlee Cluster 4 DER Wind | 48-Empress | BTF | Wind | 5 | Yes | 2021-01-11 10:00 | 4.6 | 0 | 2023-04-14
P2416 Potentia Stirling WAGF Phase 2 | 54-Lethbridge | BTF | Wind | 2 | No | 2021-01-18 10:00 | 39 | 0 | 2023-07-31
P2417 Sol Aurora Solar Battery | 33-Fort Saskatchewan | Connection | Solar + Storage | 3 | No | 2021-01-20 10:00 | 200 | 0 | 2024-04-01
P2421 RESC Big Sky Solar | 48-Empress | Connection | Solar | 3 | No | 2021-02-10 10:00 | 140 | 1 | 2024-01-01
P2422 EER Foothills MPC Solar | 46-High River | Connection | Solar | 3 | No | 2021-02-12 10:00 | 150 | 1 | 2023-06-30
P2424 ATCO Oyen 767S DER Solar | 42-Hanna | BTF | Solar | 5 | Yes | 2021-03-05 10:00 | 12.6 | 0 | 2023-04-01
P2432 Suncor TG1 & TG2 Modification | 25-Fort McMurray | BTF | Equipment Change | 5 | Yes | 2021-03-26 10:00 | 0 | 0 | 2023-07-03 | 0 | 0 | 2022-02-07
P2434 Fortis Blackmud DER Solar | 60-Edmonton | BTF | Solar | 3 | No | 2021-04-01 10:00 | 20.3 | 0 | 2024-04-01
P2435 Fortis Leduc DER Solar | 60-Edmonton | BTF | Solar | 3 | No | 2021-04-01 10:00 | 61.9 | 0 | 2024-04-01
P2436 Fortis Devon DER Solar | 60-Edmonton | BTF | Solar | 3 | No | 2021-04-01 10:00 | 20.2 | 0 | 2024-04-01
P2440 EDTI Meadowlark Modification | 60-Edmonton | Connection | Equipment Change | 5 | Yes | 2021-04-09 10:00 | 0 | 0 | 2023-02-28
P2441 Capital Power Halkirk 2 Wind | 36-Alliance/Battle River | Connection | Wind | 3 | No | 2021-04-23 10:00 | 150 | 1 | 2024-07-01
P2442 Saamis Solar Park | 04-Medicine Hat | Connection | Solar | 3 | No | 2021-04-23 10:00 | 325 | 1 | 2023-09-12
P2443 Fortis Rose Valley 635S Contract Change | 40-Wabamun | Contract | DTS | 3 | No | 2021-04-28 10:00 | 0 | -9.8 | 2026-12-31
P2445 Kiwetinohk Homestead MPC Solar | 53-Fort Macleod | Connection | Solar | 3 | No | 2021-05-03 10:00 | 400 | 1.5 | 2024-05-30
P2446 Fortis Tilley 498S DER Solar | 47-Brooks | BTF | Solar + Storage | 3 | No | 2021-05-07 10:00 | 19.6 | 0 | 2024-02-29
P2447 Greengate Luna MPC Solar Battery | 47-Brooks | Connection | Solar + Storage | 3 | No | 2021-05-13 10:00 | 465 | 1.5 | 2023-12-31
P2449 Claresholm Solar | 49-Stavely | Contract | STS | 2 | No | 2021-05-25 10:00 | 20 | 0 | 2022-12-01
P2451 Georgetown Battery Addition | 45-Strathmore/Blackie | Connection | Battery Storage | 2 | No | 2021-06-10 10:00 | 0 | 101 | 2023-08-01
P2453 EDTI Edmonton 3 H2 Plant Cogen | 60-Edmonton | Connection | Cogen | 4 | No | 2021-06-16 10:00 | 20 | 50 | 2023-11-20
P2454 Kiwetinohk Flipi MPC Gas | 30-Drayton Valley | Connection | Gas | 2 | No | 2021-06-15 10:00 | 422 | 3 | 2025-08-07
P2456 Kiwetinohk Opal Gas | 24-Fox Creek | Connection | Gas | 3 | No | 2021-06-21 10:00 | 98.5 | 0.4 | 2023-05-26
P2457 Fortis Moon Lake DER Solar | 30-Drayton Valley | BTF | Solar | 3 | No | 2021-06-23 10:00 | 16.75 | 0 | 2023-09-29
P2458 Capital Power Whitla MPC Solar | 04-Medicine Hat | Connection | Solar | 2 | No | 2021-06-24 10:00 | 88 | 1 | 2024-09-01
P2459 ENMAX Barlow Park DER Solar | 06-Calgary | BTF | Solar | 5 | Yes | 2021-06-30 10:00 | 22 | 0 | 2022-12-23
P2460 ABO Fox Meadows MPC Wind | 37-Provost | Connection | Wind | 2 | No | 2021-06-30 10:00 | 150 | 1 | 2023-12-01
P2461 Aira Solar | 04-Medicine Hat | Connection | Solar | 3 | No | 2021-07-07 10:00 | 450 | 1 | 2024-12-20
P2462 Fortis Stony Plain 434S DER Solar | 40-Wabamun | BTF | Solar | 3 | No | 2021-07-14 10:00 | 12.2 | 0 | 2023-09-29
P2464 Sunnynook Solar Battery | 43-Sheerness | Connection | Solar + Storage | 3 | No | 2021-07-21 10:00 | 280 | 100 | 2024-08-01
P2465 Enerfin Winnifred Wind Modification | 04-Medicine Hat | BTF | Wind | 2 | No | 2021-07-22 10:00 | 37.6 | 0 | 2023-07-31
P2466 PR Prominence Solar | 54-Lethbridge | Connection | Solar | 3 | No | 2021-07-22 10:00 | 80 | 1 | 2024-04-19
P2467 Pteragen Peace Butte Wind | 04-Medicine Hat | Connection | Wind | 2 | No | 2021-08-03 10:00 | 120 | 0.1 | 2025-08-25
P2468 ATCO Briker 880S DER Gas | 13-Lloydminster | BTF | Gas | 3 | No | 2021-08-09 10:00 | 3.58 | 0 | 2023-10-01
P2469 ATCO Vermilion 710S DER Gas | 13-Lloydminster | BTF | Gas | 3 | No | 2021-08-09 10:00 | 0 | 0 | 2023-10-01
P2471 Fortis Buford 538S DER Solar | 31-Wetaskiwin | BTF | Solar | 3 | No | 2021-08-11 10:00 | 15.1 | 0 | 2023-09-29
P2472 Fortis Olds 55S DER Gas | 39-Didsbury | BTF | Gas | 3 | No | 2021-08-13 10:00 | 4.9 | 0 | 2023-12-01
P2473 Fortis Provost 545S DER Gas | 37-Provost | BTF | Gas | 3 | No | 2021-08-13 10:00 | 1 | 0 | 2023-12-01
P2474 Fortis Sylvan Lake 580S DER Gas | 35-Red Deer | BTF | Gas | 3 | No | 2021-08-13 10:00 | 1.4 | 0 | 2023-12-01
P2475 EPC SS-24 DER Solar | 06-Calgary | BTF | Solar | 5 | Yes | 2021-08-13 10:00 | 22 | 0 | 2023-03-08
P2477 Fortis Monarch 492S Contract Change | 54-Lethbridge | Contract | DTS | 2 | No | 2021-08-13 10:00 | 0 | 12.1 | 2023-02-01
P2478 Fortis North Calder 37S Contract Change | 40-Wabamun | Contract | DTS | 3 | Yes | 2021-08-13 10:00 | 0 | 19.58 | 2022-12-01
P2479 Fortis Westfield 107S Contract Change | 52-Vauxhall | Contract | DTS | 2 | No | 2021-08-13 10:00 | 0 | 8.688 | 2023-02-01
P2481 TransAlta Riplinger MPC Wind | 55-Glenwood | Connection | Wind | 2 | No | 2021-08-17 10:00 | 300 | 3 | 2024-07-01
P2482 TransAlta Willow Creek 1 MPC Wind | 53-Fort Macleod | Connection | Wind | 2 | No | 2021-08-17 10:00 | 70 | 3 | 2023-07-01
P2483 TransAlta Willow Creek 2 MPC Wind | 53-Fort Macleod | Connection | Wind | 2 | No | 2021-08-17 10:00 | 70 | 3 | 2023-07-01
P2484 ATCO Thornton 2091S DER Gas | 22-Grande Cache | BTF | Gas | 3 | No | 2021-08-18 10:00 | 13.5 | 0 | 2023-09-01
P2490 TransAlta Tempest MPC Wind | 54-Lethbridge | Connection | Wind | 3 | No | 2021-09-20 10:00 | 100 | 1 | 2024-09-20
P2491 Phoenix MPC Solar | 35-Red Deer | Connection | Solar | 3 | No | 2021-09-17 10:00 | 299 | 1 | 2023-12-01
P2494 Fortis Bullshead 523S DER Solar | 04-Medicine Hat | BTF | Solar | 2 | No | 2021-09-23 10:00 | 22.3 | 0 | 2023-10-09
P2498 Fortis Hughenden 213S DER Battery | 37-Provost | BTF | Battery Storage | 5 | Yes | 2021-09-23 10:00 | 18.5 | 0 | 2022-12-16
P2499 Kiwetinohk Maskwa MPC Gas | 26-Swan Hills | Connection | Gas | 2 | No | 2021-10-08 10:00 | 450 | 2.5 | 2025-07-01
P2503 SPWC Willow Ridge Wind | 53-Fort Macleod | Connection | Wind | 2 | No | 2021-10-15 10:00 | 250 | 1 | 2023-12-20
P2504 SPWC Willow Ridge Battery | 53-Fort Macleod | Connection | Battery Storage | 2 | No | 2021-10-15 10:00 | 50 | 50 | 2023-12-20
P2506 Greengate Luna 2 MPC Solar Battery | 47-Brooks | Connection | Solar + Storage | 2 | No | 2021-10-21 10:00 | 465 | 1.5 | 2024-12-15
P2509 Kiwetinohk Granum MPC Solar | 53-Fort Macleod | Connection | Solar | 2 | No | 2021-10-29 10:00 | 400 | 1.5 | 2025-01-28
P2510 Capital Power Aldersyde Solar | 46-High River | Connection | Solar | 2 | No | 2021-10-29 10:00 | 200 | 1 | 2024-06-30
P2511 COL Chinook 181S DER Solar | 54-Lethbridge | BTF | Solar | 2 | No | 2021-11-08 10:00 | 8.75 | 0 | 2023-06-01
P2513 Shell Scotford Substation Reliability | 33-Fort Saskatchewan | Connection | Other | 3 | No | 2021-11-17 10:00 | 0 | 0 | 2024-09-01
P2514 Clem Geo Castle Meridian MPC Solar | 53-Fort Macleod | Connection | Solar | 2 | No | 2021-11-19 10:00 | 75 | 0.5 | 2023-09-01
P2515 Fortis Rimbey 297S DER Gas | 35-Red Deer | BTF | Gas | 3 | Yes | 2021-11-29 10:00 | 7.25 | 0 | 2022-12-21
P2516 Enfinite Blackie MPC Battery | 45-Strathmore/Blackie | Connection | Battery Storage | 1 | No | 2022-01-20 10:00 | 300 | 300 | 2023-12-04
P2517 Enfinite Bowmanton MPC Battery | 04-Medicine Hat | Connection | Battery Storage | 1 | No | 2022-01-20 10:00 | 500 | 500 | 2024-09-02
P2520 Enfinite Foothills MPC Battery | 46-High River | Connection | Battery Storage | 1 | No | 2022-01-20 10:00 | 400 | 400 | 2024-09-02
P2522 Enfinite Nilrem MPC Battery | 32-Wainwright | Connection | Battery Storage | 1 | No | 2022-01-20 10:00 | 150 | 150 | 2023-12-04
P2524 Shell SR Scotford Solar | 33-Fort Saskatchewan | BTF | Solar | 2 | No | 2021-11-29 10:00 | 0 | 0 | 2023-06-12
P2525 CP Genesee MPC Battery BTF | 40-Wabamun | BTF | Battery Storage | 1 | No | 2021-12-01 10:00 | 0 | 5 | 2023-09-15
P2527 TA Alberta Hydro WaterCharger Battery | 44-Seebe | Connection | Battery Storage | 2 | No | 2021-12-08 10:00 | 180 | 10 | 2023-12-01
P2528 Fortis Edmonton 95S Contract Change | 60-Edmonton | Contract | DTS | 2 | No | 2021-12-16 10:00 | 0 | 7 | 2024-04-01
P2529 EER Foothills Solar II | 46-High River | BTF | Solar | 2 | No | 2022-01-04 10:00 | 100 | 1 | 2023-08-31
P2530 Fortis Nilrem 574S DER Battery | 32-Wainwright | BTF | Battery Storage | 2 | No | 2022-01-04 10:00 | 38.2 | 0 | 2023-05-31
P2531 CEC Beddington 162S Gas | 06-Calgary | BTF | Gas | 5 | Yes | 2022-01-04 10:00 | 26 | 0 | 2023-05-12
P2532 Shell ALS1 Modification | 33-Fort Saskatchewan | BTF | Equipment Change | 5 | Yes | 2022-01-04 10:00 | 0 | 0 | 2023-05-27
P2533 Greenlight MPC Gas | 33-Fort Saskatchewan | Connection | Gas | 2 | No | 2022-01-14 | 466 | 20 | 2025-01-20
P2534 EDF Cypress 3 Wind | 04-Medicine Hat | BTF | Wind | 1 | No | 2022-01-14 10:00 | 75 | 0.97 | 2024-09-01
P2535 EDF Bull Trail 2 Wind | 04-Medicine Hat | Connection | Wind | 1 | No | 2022-01-14 10:00 | 200 | 2.74 | 2024-09-01
P2536 Fortis Ponoka 331S DER Solar Battery | 31-Wetaskiwin | BTF | Solar + Storage | 1 | No | 2022-01-25 10:00 | 18.2 | 0 | 2024-12-31
P2537 Fortis Duchess 339S DER Solar Battery | 47-Brooks | BTF | Solar + Storage | 1 | No | 2022-01-25 10:00 | 16.3 | 0 | 2024-09-01
P2538 EDTI Inland Cement Load and Reliability | 60-Edmonton | Connection | Load | 2 | No | 2022-02-01 10:00 | 0 | 7.5 | 2024-09-01
P2539 Irrigation Canal Raymond Reservoir Modification | 55-Glenwood | BTF | Equipment Change | 2 | No | 2022-02-02 10:00 | 0 | 0 | 2023-04-01
P2540 Cache Rising Sun MPC Solar | 37-Provost | Connection | Solar | 2 | No | 2022-02-04 10:00 | 125 | 1 | 2024-09-30
P2541 Fortis Peace Butte 404S DER Wind | 04-Medicine Hat | BTF | Wind | 1 | No | 2022-02-09 10:00 | 21.94 | 0 | 2025-10-01
P2543 EDTI Castle Downs Load Reliability | 60-Edmonton | Connection | Load | 2 | No | 2022-02-14 10:00 | 0 | 14.58 | 2024-06-14
P2544 PRD Halsbury Solar | 48-Empress | BTF | Solar | 2 | No | 2022-02-17 10:00 | 84 | 1 | 2023-12-31
P2545 EDF Red Rock Wind | 04-Medicine Hat | Connection | Wind | 1 | No | 2022-02-22 10:00 | 250 | 3.6 | 2024-09-01
P2546 Fortis Albchem Beaverhill Creek Load | 33-Fort Saskatchewan | Connection | Load | 2 | No | 2022-02-17 10:00 | 0 | 90 | 2024-07-26
P2548 ATCO Irish Creek 706S DER Gas | 13-Lloydminster | BTF | Gas | 3 | No | 2022-02-22 10:00 | 0.66 | 0 | 2023-10-01
P2552 Kneehill MPC Solar | 42-Hanna | Connection | Solar | 2 | No | 2022-03-04 10:00 | 450 | 2 | 2025-07-01
P2553 Dolcy Solar Battery | 37-Provost | Connection | Solar + Storage | 2 | No | 2022-03-04 10:00 | 200 | 102 | 2025-02-01
P2554 ATCO Goodfare 815S DER Battery | 20-Grande Prairie | BTF | Battery Storage | 3 | No | 2022-03-02 10:00 | 15.7 | 0 | 2023-10-01
P2555 CP Rolling Hills MPC Wind | 37-Provost | Connection | Wind | 2 | No | 2022-03-04 10:00 | 190 | 1 | 2025-06-13
P2556 Fortis High River 65S DER Solar Battery | 46-High River | BTF | Solar + Storage | 1 | No | 2022-03-04 10:00 | 17.1 | 0 | 2024-01-25
P2557 Fortis Lundbreck 513S Contract Change | 53-Fort Macleod | Contract | DTS | 3 | No | 2022-03-10 10:00 | 0 | -1.317 | 2023-02-28
P2558 Fortis Hartell 512S Contract Change | 46-High River | Contract | DTS | 3 | No | 2022-03-10 10:00 | 0 | -2.1 | 2023-02-28
P2559 Fortis Yarrow Rangeland 995S Contract Change | 55-Glenwood | Contract | DTS | 3 | No | 2022-03-10 10:00 | 0 | -2.21 | 2023-02-28
P2560 ATCO Wapiti 823S DER Battery | 20-Grande Prairie | BTF | Battery Storage | 3 | No | 2022-03-17 10:00 | 31.8 | 0 | 2023-09-15
P2562 Paintearth Wind Phase 2 | 42-Hanna | BTF | Wind | 2 | No | 2022-03-23 10:00 | 70 | 2 | 2023-07-28
P2563 EDF Pe Na Koyim Wind | 54-Lethbridge | Connection | Wind | 2 | No | 2022-03-30 10:00 | 200 | 2.88 | 2025-09-01
P2564 ATCO Bullpound 803S DER Solar | 43-Sheerness | BTF | Solar | 2 | No | 2022-04-07 10:00 | 14.3 | 0 | 2023-08-01
P2565 ATCO Three Hills 770S DER Solar | 42-Hanna | BTF | Solar | 2 | No | 2022-04-07 10:00 | 14 | 0 | 2024-07-01
P2566 Eastervale Solar Battery | 37-Provost | Connection | Solar + Storage | 2 | No | 2022-04-08 10:00 | 300 | 200 | 2025-03-01
P2568 Aura Peace Butte Solar Battery | 04-Medicine Hat | Connection | Solar + Storage | 1 | No | 2022-04-15 10:00 | 230 | 1 | 2024-04-01
P2569 Westbridge Red Willow Solar Battery | 36-Alliance/Battle River | Connection | Solar + Storage | 2 | No | 2022-04-27 10:00 | 225 | 100 | 2025-10-01
P2571 Forty Mile Granlea Modification | 04-Medicine Hat | BTF | Wind | 1 | No | 2022-05-16 10:00 | 28 | 0 | 2023-12-01
P2573 BluEarth Prairie Yarrow MPC Wind | 37-Provost | Connection | Wind | 1 | No | 2022-05-25 10:00 | 200 | 0.5 | 2024-09-01
P2574 Fortis Aura Provost DER Solar | 37-Provost | BTF | Solar | 2 | No | 2022-06-01 10:00 | 20.7 | 0 | 2023-12-01
P2575 ATCO Lindbergh Modification | 28-Cold Lake | BTF | Equipment Change | 2 | No | 2022-06-07 10:00 | 0 | 0 | 2024-01-03
P2576 Greengate Lacuna MPC Battery | 47-Brooks | Connection | Battery Storage | 1 | No | 2022-06-03 10:00 | 465 | 465 | 2024-12-01
P2577 Crossfield Hydrogen Load | 57-Airdrie | Connection | Load | 1 | No | 2022-06-06 10:00 | 0 | 35 | 2025-07-01
P2578 Montem Tent Mountain MPC Pumped Hydro | 53-Fort Macleod | Connection | Pumped Hydro Storage | 1 | No | 2022-06-06 10:00 | 400 | 400 | 2026-10-01
P2580 ATCO Swan Dive 854S Contract Change | 26-Swan Hills | Contract | DTS | 2 | No | 2022-06-07 10:00 | 0 | 1.259 | 2022-12-01
P2581 TransAlta Red Rock MPC Wind | 04-Medicine Hat | Connection | Wind | 1 | No | 2022-06-10 10:00 | 100 | 3 | 2025-07-31
P2582 Woodcroft Reliability | 60-Edmonton | Connection | Equipment Change | 2 | No | 2022-06-16 10:00 | 0 | 0 | 2025-03-25
P2583 Metiskow Pump Station Gas | 37-Provost | BTF | Gas | 1 | No | 2022-06-28 10:00 | 0 | 0 | 2024-10-01
P2584 KALiNA Energy Centre Bluesky MPC Gas | 19-Peace River | Connection | Gas | 1 | No | 2022-06-28 15:40 | 466 | 3 | 2025-09-01
P2585 MIL Generation MPC Gas | 26-Swan Hills | Connection | Gas | 1 | No | 2022-06-29 10:00 | 465 | 25 | 2026-06-01
P2586 KALiNA Energy Centre Mitsue Gas | 21-High Prairie | Connection | Gas | 1 | No | 2022-06-29 10:00 | 466 | 3 | 2026-07-01
P2587 Sunhills Solar | 40-Wabamun | Connection | Solar | 1 | No | 2022-07-07 08:03 | 130 | 1 | 2024-12-31
P2589 East Camrose MPC Solar | 31-Wetaskiwin | Connection | Solar | 1 | No | 2022-07-13 15:20 | 150 | 1 | 2025-06-01
P2590 Sunland MPC Solar Battery | 32-Wainwright | Connection | Solar + Storage | 1 | No | 2022-07-21 15:40 | 230 | 100 | 2025-04-01
P2591 Carseland 525S DER Solar | 45-Strathmore/Blackie | BTF | Solar | 1 | No | 2022-07-21 16:15 | 19 | 0 | 2024-03-01
P2592 Big Rock Solar Battery | 46-High River | Connection | Solar + Storage | 1 | No | 2022-07-25 10:22 | 100 | 40 | 2025-05-15
P2594 Ruth Lake 848S Contract Change | 25-Fort McMurray | Contract | STS | 2 | No | 2022-07-26 11:20 | 50 | 0 | 2023-04-01
P2595 CastorWest Solar | 42-Hanna | Connection | Solar | 1 | No | 2022-07-29 15:49 | 47 | 0.75 | 2024-10-01
P2597 Riverbend 618S Contract Change | 54-Lethbridge | Contract | DTS | 1 | No | 2022-08-18 09:24 | 0 | 7.58 | 2023-02-01
P2598 Legal Solar | 60-Edmonton | Connection | Solar | 1 | No | 2022-08-25 15:14 | 125 | 0.75 | 2024-10-01
P2600 Spruce Grove North Solar | 60-Edmonton | Connection | Solar | 1 | No | 2022-08-25 15:58 | 220 | 0.75 | 2024-10-01
P2601 Heritage MPC Wind | 53-Fort Macleod | Connection | Wind | 1 | No | 2022-08-30 16:05 | 300 | 3 | 2025-09-01
P2602 Little Flipi MPC Gas | 35-Red Deer | Connection | Gas | 1 | No | 2022-08-31 16:30 | 117 | 0.5 | 2025-09-01
P2603 Flatbush 500S Contract Change | 27-Athabasca/Lac La Biche | Contract | DTS | 1 | No | 2022-09-08 10:39 | 0 | -1.6 | 2023-03-01
P2604 Flatbush 500S Contract Change | 27-Athabasca/Lac La Biche | Contract | DTS | 1 | No | 2022-09-08 10:53 | 0 | 1.481 | 2023-03-01
P2608 Fort Macleod 15S Contract Change | 53-Fort Macleod | Contract | DTS | 1 | No | 2022-09-13 11:10 | 0 | -4.8 | 2022-12-01
P2609 Fort Macleod 15S Contract Change | 53-Fort Macleod | Contract | DTS | 1 | No | 2022-09-13 10:58 | 0 | 4.8 | 2022-12-01
P2612 Hand Hills Battery | 42-Hanna | BTF | Battery Storage | 1 | No | 2022-09-22 09:32 | 10 | 0 | 2025-03-03
P2613 Border Solar Battery | 48-Empress | Connection | Solar + Storage | 1 | No | 2022-10-03 10:10 | 250 | 60 | 2024-12-01
P2614 Dow Fort Sask. Load | 33-Fort Saskatchewan | Connection | Wasteheat | 1 | No | 2022-09-28 14:50 | 84 | 140 | 2026-08-15
P2615 Datacenters Balzac Load | 57-Airdrie | Connection | Load | 1 | No | 2022-10-05 11:43 | 0 | 75 | 2025-06-01
P2625 Hays Solar 2 Battery | 52-Vauxhall | Connection | Solar + Storage | 1 | No | 2022-11-04 12:43 | 185 | 0.2 | 2024-09-01
P2628 Foster Creek Load | 28-Cold Lake | Connection | Load | 1 | No | 2022-11-07 15:41 | 0 | 41 | 2024-01-01
P2629 Taber Solar | 52-Vauxhall | BTF | Solar | 1 | No | 2022-11-09 11:11 | 45 | 0 | 2024-10-01
P2630 Berland River Load | 29-Hinton/Edson | Connection | Load | 1 | No | 2022-11-14 14:09 | 0 | 37 | 2025-09-01
P2631 Smoky River MPC Wind | 19-Peace River | Connection | Wind | 1 | No | 2022-11-14 11:26 | 160 | 1 | 2025-10-01
ISD Under Review
P1500 Renewable Energy Service WAGF | 53-Fort Macleod | Connection | Wind | 5 | No | 2013-11-18 10:00 | 47 | 1 | Under Review
P1505 ATCO City of Grande Prairie New POD | 20-Grande Prairie | Connection | Load | 5 | Yes | 2013-12-10 10:00 | 0 | 27 | Under Review
P1864 BowArk Drywood Battery | 55-Glenwood | Connection | Battery Storage | 5 | No | 2016-09-30 10:00 | 33.9 | 1 | Under Review
P2195 FortisAlberta Bassano 435S DER Solar | 47-Brooks | BTF | Solar | 5 | Yes | 2019-01-07 10:00 | 9.25 | 0 | Under Review
P2216 FortisAlberta Chappice Lake 649S DER Solar | 04-Medicine Hat | BTF | Solar | 5 | Yes | 2019-03-22 10:00 | 10.5 | 0 | Under Review
P2323 Fortis Taber 83S DER Solar 1 | 52-Vauxhall | BTF | Solar | 2 | No | 2020-02-06 10:00 | 16.4 | 0 | Under Review
P2324 Fortis Taber 83S DER Solar 2 | 52-Vauxhall | BTF | Solar | 2 | No | 2020-02-06 10:00 | 15 | 0 | Under Review
P2325 Fortis Taber 83S DER Solar 3 | 52-Vauxhall | BTF | Solar | 2 | No | 2020-02-06 10:00 | 13.3 | 0 | Under Review
P2326 Fortis Taber 83S DER Solar 4 | 52-Vauxhall | BTF | Solar | 2 | No | 2020-02-06 10:00 | 9.2 | 0 | Under Review
P2373 Kirkcaldy MPC Solar | 49-Stavely | Connection | Solar | 3 | No | 2020-08-14 10:00 | 350 | 2 | Under Review
P2418 Greencells Estuary Solar | 48-Empress | Connection | Solar | 3 | No | 2021-01-28 10:00 | 200 | 1.5 | Under Review
P2452 ATCO Poplar Hill 790S DER Gas | 20-Grande Prairie | BTF | Gas | 3 | No | 2021-06-10 10:00 | 5 | 0 | Under Review
P2593 Forty Mile Wind Phase 2 | 04-Medicine Hat | BTF | Wind | 1 | No | 2022-07-22 10:33 | 134 | 0 | Under Review
On Hold
P1770 NextEra Red Deer Battery Energy Storage System | 42-Hanna | Connection | Battery Storage | 2 | No | 2016-03-18 10:00 | 40 | 46 | On Hold
P1772 Ghost Pine Battery Energy Storage System | 42-Hanna | BTF | Battery Storage | 2 | No | 2016-03-18 10:00 | 0 | 34.7 | On Hold
P1885 Joss Wind Northern Lights WAGF | 26-Swan Hills | Connection | Wind | 2 | No | 2016-11-01 10:00 | 400 | 3 | On Hold
P1891 Archer Piikani Solar | 53-Fort Macleod | Connection | Solar | 2 | No | 2016-11-07 10:00 | 40 | 0.1 | On Hold
P1913 Glenridge Wind | 48-Empress | Connection | Wind | 2 | No | 2017-01-19 10:00 | 150 | 1 | On Hold
P1928 RealPart Calgary Area Solar | 06-Calgary | Connection | Solar | 2 | No | 2017-03-24 10:00 | 150 | 0.3 | On Hold
P2007 Chiniki Solar | 44-Seebe | Connection | Solar | 2 | No | 2017-10-02 10:00 | 40 | 0.3 | On Hold
P2068 Four Rivers Wind | 04-Medicine Hat | Connection | Wind | 2 | No | 2018-03-26 10:00 | 450 | 0.5 | On Hold
P2124 Northland Bow City MPC Solar | 47-Brooks | Connection | Solar | 2 | No | 2018-07-11 10:00 | 400 | 2 | On Hold
P2138 Quill Rocky Mountain Gas | 30-Drayton Valley | Connection | Gas | 2 | No | 2018-08-20 10:00 | 150 | 0.5 | On Hold
P2140 PBC Paul Band Solar | 40-Wabamun | Connection | Solar | 2 | No | 2018-08-20 10:00 | 37 | 0.5 | On Hold
P2176 FortisAlberta Acheson 305S DER Solar | 60-Edmonton | BTF | Solar | 2 | No | 2018-10-29 10:00 | 8.5 | 0 | On Hold
P2177 FortisAlberta Red Deer 63S DER Solar | 35-Red Deer | BTF | Solar | 2 | No | 2018-10-31 09:00 | 18.3 | 0 | On Hold
P2211 ENGIE Buffalo Trail South MPC Wind | 04-Medicine Hat | Connection | Wind | 2 | No | 2019-02-25 10:00 | 200 | 6 | On Hold
P2227 FortisAlberta Mearns Area Load | 60-Edmonton | Connection | Load | 2 | No | 2019-04-23 10:00 | 0 | 24.1 | On Hold
P2228 FortisAlberta Sangudo Area Load | 40-Wabamun | Connection | Load | 2 | No | 2019-04-23 10:00 | 0 | 26 | On Hold
P2229 FortisAlberta Whitecourt Area Load | 26-Swan Hills | Connection | Load | 2 | No | 2019-04-23 10:00 | 0 | 20 | On Hold
P2238 Pembina CDH Load | 33-Fort Saskatchewan | Connection | Load | 2 | No | 2019-06-03 10:00 | 0 | 27.5 | On Hold
P2256 ATCO Poplar Hill Load | 20-Grande Prairie | Connection | Load | 2 | No | 2019-07-11 10:00 | 0 | 67.9 | On Hold
P2269 Sunset Solar | 52-Vauxhall | Connection | Solar | 2 | No | 2019-08-28 10:00 | 60 | 0.26 | On Hold
P2290 ATCO Bridge Creek 798S DER Gas | 20-Grande Prairie | BTF | Gas | 2 | No | 2019-10-23 10:00 | 0 | 0 | On Hold
P2297 FortisAlberta Burdett 368S DER Solar Battery Storage | 52-Vauxhall | BTF | Solar + Storage | 2 | No | 2019-11-15 10:00 | 17.5 | 0 | On Hold
P2303 Nose Hill MPC Wind | 42-Hanna | Connection | Wind | 2 | No | 2019-12-03 10:00 | 98 | 1.5 | On Hold
P2316 Pembina Duvernay Cogen | 24-Fox Creek | Connection | Cogen | 2 | No | 2020-01-21 10:00 | 30 | 17 | On Hold
P2340 TransAlta Sundance Unit 5 Gas | 40-Wabamun | Connection | Gas | 2 | No | 2020-03-20 10:00 | 774.6 | 15 | On Hold
P2380 ATCO Updike 886S DER Gas | 20-Grande Prairie | BTF | Gas | 2 | No | 2020-09-08 10:00 | 20.4 | 0 | On Hold
P2386 ATCO Ksituan River 754S DER Gas | 20-Grande Prairie | BTF | Gas | 2 | No | 2020-09-24 10:00 | 38.4 | 0 | On Hold
P2430 Greengate Midnight MPC Solar Battery | 04-Medicine Hat | Connection | Solar + Storage | 2 | No | 2021-03-26 10:00 | 465 | 1.5 | On Hold
P2438 Federation Marguerite Lake CAE Storage | 28-Cold Lake | Connection | Compressed Air Energy Storage | 2 | No | 2021-04-07 10:00 | 320 | 125 | On Hold
P2463 BluEarth Bindloss MPC Solar Battery | 48-Empress | Connection | Solar + Storage | 2 | No | 2021-07-15 10:00 | 120 | 21 | On Hold
P2470 Fortis West Brooks 28S DER Solar | 47-Brooks | BTF | Solar | 2 | No | 2021-08-11 10:00 | 22 | 0 | On Hold
P2488 NGCI Ermineskin Cree Nation Solar | 31-Wetaskiwin | Connection | Solar | 2 | No | 2021-09-07 10:00 | 80 | 0.5 | On Hold
Recently Energized
P1533 Joss MPC WAGF | 48-Empress | Connection | Wind | 5 | Yes | 2014-03-01 | 122.4 | 1 | 2022-11-29
P1698 Joss Jenner WAGF - Phase 2 | 48-Empress | BTF | Wind | 5 | Yes | 2015-09-08 10:00 | 71.4 | 1 | 2022-11-29
P1831 Fortis 255S Vulcan Faribault Farms DG PV | 49-Stavely | BTF | Solar | 6 | Yes | 2016-08-05 10:00 | 17 | 0 | 2022-09-26
P1898 Pattern Lanfine North Wind | 42-Hanna | Connection | Wind | 6 | Yes | 2016-12-02 10:00 | 145 | 1.5 | 2022-11-14
P1909 Garden Plain Wind | 42-Hanna | Connection | Wind | 6 | Yes | 2016-12-22 10:00 | 130 | 4 | 2022-04-28
P2059 ATCO Three Hills 770S DER Solar 1 | 42-Hanna | BTF | Solar | 6 | Yes | 2018-02-20 10:00 | 14 | 0 | 2022-11-01
P2061 ATCO Michichi Creek 802S DER Solar | 42-Hanna | BTF | Solar | 6 | Yes | 2018-02-20 10:00 | 11 | 0 | 2022-11-01
P2234 Jenner Wind Phase 3 | 48-Empress | BTF | Wind | 5 | Yes | 2019-05-10 10:00 | 109.2 | 1 | 2022-11-29
P2235 Pembina Empress Cogen | 48-Empress | BTF | Cogen | 6 | Yes | 2019-05-08 10:00 | 0 | 0 | 2022-06-11 | 0 | 0 | 2022-09-14
P2242 ATCO Sarah Lake 743S DER Geothermal | 26-Swan Hills | BTF | Gas | 6 | Yes | 2019-06-13 10:00 | 12.95 | 0 | 2022-09-08
P2254 RESC Hilda MPC Wind | 48-Empress | Connection | Wind | 6 | Yes | 2019-07-08 10:00 | 100 | 3 | 2022-11-16
P2263 BER Hand Hills MPC Wind | 42-Hanna | Connection | Wind | 6 | Yes | 2019-08-02 10:00 | 150.8 | 0.15 | 2022-09-30
P2305 Capital Power Genesee 3 Change | 30-Drayton Valley | BTF | Gas | 6 | Yes | 2019-12-11 10:00 | 6 | 0 | 2022-11-12
P2317 FortisAlberta High River 65S DER Gas | 46-High River | BTF | Gas | 5 | Yes | 2020-01-24 10:00 | 6.9 | 0 | 2022-11-01
P2362 Fortis Enchant 447S DER Solar | 52-Vauxhall | BTF | Solar | 5 | Yes | 2020-07-16 10:00 | 22 | 0 | 2022-10-14
P2363 Fortis Enchant 447S DER Solar | 52-Vauxhall | BTF | Solar | 5 | Yes | 2020-07-16 10:00 | 17.9 | 0 | 2022-10-14
P2364 Fortis Enchant 447S DER Solar | 52-Vauxhall | BTF | Solar | 5 | Yes | 2020-07-16 10:00 | 9.3 | 0 | 2022-10-26
P2365 Fortis Enchant 447S DER Solar | 52-Vauxhall | BTF | Solar | 5 | Yes | 2020-07-16 10:00 | 22.7 | 0 | 2022-10-26
P2381 Capital Power Genesee Unit 3 Change | 40-Wabamun | BTF | Other | 6 | Yes | 2020-09-10 10:00 | 0 | 0 | 2022-11-12
P2413 EDF Cypress 2 Wind | 04-Medicine Hat | BTF | Wind | 5 | Yes | 2021-01-07 10:00 | 45.78 | 0.62 | 2022-11-21 |  |  | 2022-12-13
P2485 Fortis Wabamun 2739S & Carvel 432S Contract Change | 40-Wabamun | Contract | DTS | 6 | Yes | 2021-08-25 10:00 | 0 | 0 | 2022-11-01
P2549 CNRL Horizon Mining 838S Contract Change | 25-Fort McMurray | Contract | DTS | 6 | Yes | 2022-02-23 10:00 | 0 | -15 | 2022-09-28
P2550 CP Genesee GN2 Modification | 40-Wabamun | BTF | Coal | 6 | Yes | 2022-02-25 10:00 | 20 | 0 | 2022-10-01
P2572 Heartland BR5 Contract Change | 36-Alliance/Battle River | Contract | STS | 6 | Yes | 2022-05-18 10:00 | 10 | 0 | 2022-10-01
Recently Cancelled
P2096 CKPC Petrochemical Facility | 33-Fort Saskatchewan | Connection | Load | 3 | No | 2018-05-24 10:00 | 0 | 80 | Cancelled
P2119 FortisAlberta Coleman Area Capacity and Reliability | 53-Fort Macleod | Connection | Load | 3 | No | 2018-07-04 10:00 | 0 | 12.9 | Cancelled
P2266 ATCO Seal Lake 869S DER Solar | 19-Peace River | BTF | Solar | 5 | No | 2019-08-14 10:00 | 2.1 | 0 | Cancelled
P2372 Fortis High River 65S DER Gas | 46-High River | BTF | Gas | 3 | No | 2020-08-12 10:00 | 3.4 | 0 | Cancelled
P2398 Invenergy Schuler Wind | 48-Empress | Connection | Wind | 2 | No | 2020-11-23 10:00 | 150 | 2 | Cancelled
P2487 ATCO Sturgeon 734S DER Battery | 23-Valleyview | BTF | Battery Storage | 2 | No | 2021-08-27 10:00 | 18.8 | 0 | Cancelled
P2551 Red Deer MPC Solar | 35-Red Deer | Connection | Solar | 1 | No | 2022-03-04 10:00 | 450 | 2 | Cancelled
P2579 Pembina Empress Solar | 48-Empress | BTF | Solar | 1 | No | 2022-06-07 10:00 | 5 | 0 | Cancelled
P2599 Cardiff MPC Solar | 60-Edmonton | Connection | Solar | 1 | No | 2022-08-25 15:28 | 80 | 0.75 | Cancelled